|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
|  |  |

 | **Project Status Report**Initiative-163: Upgrade MeridianAs of 11/22/2021 | **Project Manager:** Dan Boulger**Project Sponsor:** Matt Doyle |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 163 | **ETSC Priority:** N/A | **Project Scheduled Completion Date:** 01/05/2021 | **Project Lifecycle:** Execution |
| **Project Description:** Upgrade Meridian to version 20.2 |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **YELLOW = Moderate issues** | **Resources:** | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **Schedule End Date** | **Actual****End Date** | **% Complete** | **Actions/Comments** |
| Configure Meridian in stage environment | 03/08/2021 | 04/01/2021 | 04/01/2021 | 100% |  |
| Upgrade and configure Meridian in development environment | 04/01/2021 | 06/22/2021 | 08/17/2021 | 100% |  |
| Dev environment System testing | 07/30/2021 | 08/06/2021 | 08/18/2021 | 100% |  |
| Gather requirements, develop and test employee data integration | 04/13/2021 | ~~10/04/2021~~12/06/2021 |  | 95% | Testing is in progress. |
| Upgrade and configure Meridian in test environment | 06/07/2021 | 09/06/2021 | 09/02/2021 | 100% |  |
| Test environment System testing | 08/19/2021 | 09/13/2021 | 09/13/2021 | 100% |  |
| Data clean-up | 08/13/2021 | ~~09/04/2021~~~~11/12/2021~~12/13/2021 | 12/09/2021 | 100% |  |
| Complete UAT/develop training materials | 09/02/2021 | ~~11/29/2021~~12/17/2021 | 12/17/2021 | 100% |  |
| Upgrade and configure Meridian in production | TBD | ~~12/14/2021~~01/05/2021 |  | 10% | Implementation plan is being developed. |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** |
| --- | --- | --- |
|  | * Re-created current Meridian version in the test environment.
* Ran cleanup script against Meridian in the test environment
* Validated data cleanup
* Ran cleanup script against Meridian in the production environment
* Completed employee data integration development
* Completed UAT & developing training material
 | * Continue employee data integration testing
* Continue production implementation planning
 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| No Key Decisions to Report |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Risks** | **Probability** | **Impact** | **Status** |
| Go-live date has not been confirmed with vendor. The go live date will depend on vendor availability. | Moderate | Moderate | Vendor is unavailable for upgrade during the holiday season. We are looking to get on their calendar for early next year. |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| Issue #1: Due to a technical issue, the vendor took longer to complete the Meridian installation in our dev server than planned. The schedule has been adjusted to account for this delay. | High | High | **Resolved.**  |
| Issue #2: Training was missed as a task in the project schedule.  | High | High | **Resolved.** The schedule has been adjusted to account for this oversight delay. |
| Issue #3: Vendor initially indicated that we could run the cleanup script against the new version of Meridian, but contradicted that statement after delivering the script. We must re-create the existing Meridian version in the test environment to run and test the script.  | Moderate | High | **Resolved.** We re-created the existing Meridian version in the test environment, ran, and tested the script. We ran the script against the production database. The issue is successfully resolved. |
| Issue #4: The employee data integration task took longer than initially planned. | High | High | **Resolved.** The schedule has been adjusted to account for this delay. |