|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
|  |  |

 | **Project Status Report**Initiative-149: Rewrite LIMS ReportsAs of 06/03/2022 | **Project Manager:** Shabab Shams**Project Sponsor:** Srivi Ramamurthy |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 149 | **ETSC Priority:** N/A | **Project Scheduled Completion Date:** 12/2021 | **Project Lifecycle:**  **Closed** |
| **Project Description:** Rewrite LIMS Actuate Reports into Telerik Format |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **GREEN = No issues** | **Resources:** | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **Schedule End Date** | **Actual****End Date** | **% Complete** | **Actions/Comments** |
| Initiation | 01/12/2021 | 02/14/2021 | 02/14/2021 | 100% | Approved Project Charter |
| Planning | 02/15/2021 | 03/15/2021 | 03/15/2021 | 100% | Work Plan out for Review |
| Execution | 03/15/2021 | 12/31/2021 | 05/20/2022 | **100%** | All reports converted and deployed in production |

**Completion Date: 05/20/2022**

**Number of Reports by Status:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **COMPLETED** | **IN UAT** | **IN DEVELOPMENT** | **IN QUEUE** | **TOTAL REPORTS** |
| **77** | **0** | **0** | **0** | **77** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| Add Phani Kotla as additional resource (developer) | Dan Boulger | Approved | Decided – 04/01/2021 |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Risks** | **Probability** | **Impact** | **Status** |
| Final report is taking more time than expected | High | High | There are two issues left (below). Vendor working on them to resolve. |
| LIMS Application version 12.9 and Oracle 12.1 both become unsupported by vendor by July 2022. | Realized | High | Report conversion in progress. Once all reports are converted to Telerik, LIMS and Oracle can be upgraded to supported version. |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |