## Slide 1
SASD Maximo Ecosystem Upgrade
Initiative – 166
09/14/2022 Status Meeting

## Slide 2
Agenda
Last 61 days
Next 45 days
Risk Log
1
5
2
3
4
Q&A
6
Mitigated Risks
Load/Performance Test

## Slide 3
Spatial re-configuration and widget development is still 95% complete.
Completed Maximo TEST environment
Completed GIS TEST environment.
Sandbox environment is 50% complete.
The last 61 days:
Completed User Acceptance Testing prep work for non-spatial related items.
Completed prep work for Core Maximo load testing.
Non-Spatial integrations have been validated in TEST

## Slide 4
Conducted load/performance test on Core Maximo.
Started to configure Maximo in Production (App Servers)
Started User Acceptance Testing for non-spatial related integrations and functions.
Continue to configure Day Off Database in TEST
The last 61 days (continued)

## Slide 5
Load/Performance Test on Core Maximo 09/08/2022

## Slide 6
Developed multiple user journeys to simulate what a user would do inside Maximo.
Up to 250 bots simulated a load on the system. This simulates 250 users actively working in Maximo.
Ran multiple dry runs to pre-tune our environment prior to our full test on 9/8/2022.
Ran a total of 6 different load/performance tests throughout the 16 hour session. These test included maximum load “spike” tests and endurance tests.
Core Maximo Load/Performance Test Details
Added additional resources to our VM SQL Cluster. 2 CPUs and 14 additional GBs of RAM.
Don Keene and his test team logged into the system during the load test to see what actual performance looked like.
Dropped down to 30 concurrent users putting a load onto the system and slowed down the robots to human speed.

## Slide 7
The Bottleneck
If we were waiting to get seated at a restaurant. A table for a party of two will be more available/ready sooner than a table for a party of six people. The party of six will have to wait for all 6 chairs to be available before they can sit down.
This is the same situation for “CPU Ready”. It has to wait for all the CPU’s assigned to a VM to be available in order for the VM to execute the next command.

## Slide 8
Technical Explanation
“CPU Ready” state: a vSphere metric that records the amount of time a VM is ready to use CPU but was unable to schedule physical CPU time because all the vSphere ESXi host CPU resources are busy.
The Performance issue we encountered was the “CPU Ready” state. Because of the way the virtualization environment works, all the CPU’s are shared to all VM’s running on the host hardware/server. In order for a 6 CPU VM to execute it’s commands, it needs all six CPU’s to be available at the same time to execute.
We encountered up to 14870ms (14.87 seconds) on the SQL server. This was our biggest hitter on performance. This means the VM waited up to 15.87 seconds to execute it’s commands at some point in time.
The application servers ranged from 2000ms to 7500ms. Quite a bit less than the SQL server but was also a minor factor in the slowness. These are less critical as they can be tuned back.

## Slide 9
Continue User Acceptance Testing
Complete validation of data synchronization process in TEST
Validate spatial reconfiguration and widget in TEST
Continue to build out Maximo PROD
The next 45 days
Prep for Load/Performance Test #2 on physical hardware and with Spatial fully configured in TEST

## Slide 10
# | Description | Status
8 | Spatial re-configuration and widget development is behind. | Starboard is preparing to move their work into the TEST environment. With the go live date of 11/7/2022 being pushed due to load/performance test failing, Starboard will have time to catch up.
19 | Weather App data source is end of life. | New data source (API) has been purchased and will be implemented prior to production roll out.
20 | SQL Virtual Cluster may not meet customer performance requirements for Production. | Issue is resolved. Did not pass load/performance test on 9/8/2022. Decision is logged to not move forward to production on VM SQL Cluster.
21 | County 311 integration will not be completed by our go live date of 11/7/2022 | Since we are not moving to production on 11/07/2022 due to load test issue, this will give CPI enough time to build the integration.
Risks mitigated since last status meeting

## Slide 11: Initiative-166 Open Risks
# | Description | Status
7 | Physical SQL server hardware is still back-ordered | Open ETA is now 10-24-2022
17 | Cost for Maven support will increase if we do not complete this project by end of 2022 | Open – Low impact. Confirmed with Maven that the increase will $5.00 per hour.
18 | Not enough support hours included in the contracts to complete the project. | Continuing to monitor this resource
22 | Weather App data source in current production will be end of life before we can move to production with the new Maximo. | Will need to update the weather API in the current production environment. Will discuss with team on how to move forward with this.

## Slide 12
# | Description | Status
23 | Due to delays with moving to PROD, we may run into the need to apply security patches to Maximo. | This would require additional work to validate the patch in DEV and TEST. Depending on the patch, we may have to do some UAT again.
24 | Project resources being idle | Due the duration of this project, resources may not be available when we are ready to move to production once hardware is in place.
Initiative-166 Open Risks (Continued)

## Slide 13
High Level Schedule
Milestone | Completion Target Date | Status
Complete Spatial Re-configuration and widget re-design in DEV (Starboard) | 8/26/2022 | Behind ETA is 9/16/22
Complete TEST environment (Maximo, GIS, Spatial) | 8/31/2022 | 95% (Spatial is behind)
Complete User Acceptance Testing (UAT) in TEST (extended 1 week) | 10/03/2022 | In Progress (might be impacted by Spatial)
Go Live weekend (on VMs) Pushed 1 week due to Halloween | 11/07/2022 | ETA for hardware is 10/24/22
Migrate to physical hardware | TBD | ???????

## Slide 14
SASD Projects and Efforts on Hold
Business Planning
  Underground Facility Claims module in Maximo
Information Management
  ArcGIS Field Maps for Insect Mitigation implementation and development
  ArcGIS Pro integration
  CMMS Evaluation
  Enterprise/Portal final implementation
  Hiring GIS Analyst I/II
  Migration from ArcPad to StudioGo final implementation
Pipeline Support
  Granite upgrade
Evaluation of the Max_report list (currently 1,400 reports)
Several Change Advisory Committee (CAT) items implementation related to new tools to improve work efficiency and additional functionality in Maximo, impacting SASD across the board