## Slide 1
SASD Maximo Ecosystem Upgrade
Initiative – 166
06/01/2022 Status Meeting

## Slide 2
Agenda
True scope of this project.
Last 30 days
Next 30 days
Risk Log
Schedule?
1
5
2
3
4
6
Q&A

## Slide 3
Initiative-166
is not just Maximo
SASD
Maximo
Ecosystem
Maximo
7.6.1.2
Maximo
Spatial
Config
New Technologies
Integrations
(13)
Data Synchronization/GIS
Granite

## Slide 5
Matrix main resources into one core project team. One team with one goal.
Team members and vendors were given access to toolset. Jira, Confluence, and Slack
Streamlined communication and meetings to keep working groups focused. Communicated roles and responsibilities.
Removed as many roadblocks as we could for the team.
The last 30 days
Maximo Development environment is now online.
Spatial configuration has started in DEV
Most integrations have been validated in DEV

## Slide 6
Spatial/GIS configuration will continue in DEV.
Onboard team members in toolset. (basic training)
Analyze risk log and develop mitigation plans
Begin work on Maximo TEST environment
The next 30 days: Continue to build momentum!
Increase the pace for our vendors. Define vendor tasks and fine tune their schedule
Start to layout User Acceptance Test plans
Begin to fine tune our schedule based on the complete body of work

## Slide 7: Initiative-166 Open Risks
# | Description | Status
7 | Physical SQL server hardware is still back-ordered | Open – ETA July 7th 2022
8 | Spatial Configuration project is behind | Open
9 | The GIS DEV Application server is Windows server 2012 and has an EOL date of 10/1/2023 | Open
11 | Granite compatibility with SQL 2019 | Open
12 | DTECH SQL Support Hours - Possibly not enough available | Will be mitigated soon.
13 | IBM Extended Support contract is not in place due to a mistake by IBM | Will be mitigated soon.
14 | George Nordgreen is no longer the Product Owner for Granite | Open
15 | The 3Par Storage Hard Drives will be end of life October 31st, 2022. No extended support is available | Open
16 | Alletra Storage system replacing the 3Par will not be in house until (Gene will provide ETA) | Open
17 | Cost for Maven support will increase if we do not complete this project by end of 2022 | Open
18 | Not enough support hours included in the contracts to complete the project. (Maven and Starboard) | Open

## Slide 8
June
July
August
Sept
Oct
Nov
Dec
2022
Schedule?