|  |  |  |
| --- | --- | --- |
| D:\SASD RegionalSan\Joint Logo.png | **Project Status Report**  **Application Rationalization**  As of  **08/30/2021** | **Project Manager:** Rudy Aguillio  **Project Sponsor:** Dan Boulger |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Initiative Number:** 182 | | **ETSC Priority:** N/A | | **Project Scheduled Completion Date:** 03/31/2022 | | | **Project Lifecycle:**  Execution | |
| **Project Description:** Analyzing application costs and high-level business requirements seeking opportunities to reduce the IT Budget. | | | | | | | | |
| **Scope:** | **GREEN = No Issues** | | **Schedule:** | | **GREEN = No Issues** | **Resources:** | | **GREEN = No Issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **Schedule End Date** | **Actual**  **End Date** | **% Complete** | **Actions/Comments** |
| All Phase 2a Meetings have been scheduled | 05/30/21 | 05/30/21 | 05/30/21 | 100% |  |
| Phase 2a meetings have been completed | 06/01/21 | 07/31/21 | 07/23/21 | 100% |  |
| Schedule all Phase 2b Meetings | 07/31/21 | 10/15/21 | TBD | 40% | * Scheduled Meetings through 09/08. |
| Complete Phase 2b Meetings: HLRs and BPMs | 08/01/21 | 03/30/22 | TBD | 15% |  |

| **IT Task #** | **Completed Activities/Issues This Reporting Period** | **Planned Activities for Next Reporting Period** | |
| --- | --- | --- | --- |
| IT-3443 | * Completed all Phase 2a Meetings | | * Continue to conduct Phase 2b meetings * Prioritize base on INIT-166 and INIT-143 Configuration Impacted Applications |
| TBD | Continue scheduling and executing Phase 2b Meetings:  Andrea is also working on the Maximo Upgrade Initiatives. She will be prioritizing those related applications in the scheduling process. | | * Document HLR Requirements * Document As-IS Business Process Models (BPM) for Phase 2b |
| TBD | ERP Next Steps: Completed Draft for District Engineer Presentation | | * Continue Project Plan Draft * Schedule DE presentation * Continue Build-Out of Jira Big Picture to coincide with Planning Epics/Tasks/Sub-Tasks |
|  |  | |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Risks** | **Probability** | **Impact** | **Status** |
| No Risks Identified |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |