|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  |  | | **Project Status Report**  Initiative-183: ITSD Portal  As of 01/14/2022 | **Project Manager:** Elizabeth White  **Project Sponsor:** Jeff Vail |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Initiative Number:** 183 | | **ETSC Priority:** N/A | | **Project Scheduled Completion Date:** 02/04/2022 | | | **Project Lifecycle:**  Execution | |
| **Project Description:** Re-designing the current IT Service Desk Portal to better align with the changes IT is making to our current intake process flows. | | | | | | | | |
| **Scope:** | **GREEN = No issues** | | **Schedule:** | | **GREEN = No issues** | **Resources:** | | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **Schedule**  **End Date** | **Actual**  **End Date** | **% Complete** | **Actions/Comments** |
| Planning |  |  |  | 100% |  |
| * Project Work Plan | 08/03/2021 | N/A |  |  | Continuous updates |
| Execution |  |  |  |  |  |
| * Sprint Planning & Development |  |  |  | 100% | Tracked in Initiative-173 |
| * System Test, Portal | 12/20/2021 | 12/30/2021 | 01/04/2022 | 100% |  |
| Implementation |  |  |  |  |  |
| * Documentation | 11/29/2021 | 01/31/2021 |  | 75% |  |
| * Communication Plan | 07/14/2021 | 12/18/2021 | 1/14/2022 | 100% |  |
| * Training | 12/30/2021 | 01/31/2022 |  | 50% | In-progress |
| * Implementation Planning | 01/04/2022 | 01/31/2022 |  | 80% | In-progress |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** | |
| --- | --- | --- | --- |
| IT-3684  IT-3817 | Completed system testing, task closed.  Conducted implementation planning meetings on 1/4/2022 and 1/10/2022.  Documented the IT Service Desk Cut-Over Plan. | | * Continue work on training manual & tutorials * Continue working on implementation tasks contained within the IT Service Desk Cut-Over Plan |

<https://confluence.sacsewer.com/display/INIT183/Risk+Log>

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Risks** | **Probability** | **Impact** | **Status** |
| No risks have been identified. | High | High | Open |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |