|  |  |  |
| --- | --- | --- |
|  | **Project Status Report** **Develop RFP for ERP System****As of 10/02/2022** | **Project Manager: Arshad Waheed****Project Sponsor:** Jeff Vail**Business Owner:** Matt Doyle |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number: 195** | **Priority:** High | **Project Scheduled Completion Date:** November 17, 2023 (Estimated) | **Project Lifecycle:**  Pre-initiation |
| **Project Description:** Develop RFP for procurement and implementation of an ERP system using services of a qualified and experienced vendor (Consulting company). The Consulting company shall evaluate ERP needs of the Districts and help develop an RFP for selection of an ERP system. The selected consulting company shall aso assist the Districts in the selection process pertaining to the ERP software. After separation from the County of Sacramento, the Districts may not be able to continue the use of COMPASS and shall need its own ERP system for its business. |
| **Scope:** | **GREEN = No Issues** | **Schedule:** | **GREEN = No Issues** | **Resources:** | **Green = No Issues** |
| **Milestones** | **Start Date** | **End Date** | **Actual****End Date** | **% Complete** | **Actions/Comments** |
| Prepare RFP for procurement of outside consulting services | 05/16/2022 | 06/15/2022 | 06/14/2022 | 100% | Assigned resources: Arshad WaheedTask status: Completed |
| RFP issued for procurement of consulting services | 06/15/2022 | 06/15/2022 | 06/15/2022 | 100% | Assigned resources: Arshad WaheedTask status: Completed |
| Bidders Conference | 06/30/2022 | 06/30/2022 | 06/30/2022 | 100% | Assigned resources: Arshad WaheedTask status: Completed |
| Eight (8) Bids/Proposals received | 07/20/2022 | 07/20/2022 | 07/20/2022 | 100% | Assigned resources: Arshad WaheedTask status: Completed |
| Perform and complete Evaluation ofProposals / Bids to select the most suitable consulting company in terms of qualifications and experience | 08/01/2022 | 09/30/2022 | 09/27/2022 | 100% | A six (6) member evaluation committee was notified to complete the task of evaluating proposals and deliberate with each other to select the most suitable consulting company.Evaluation team: Kerri Stewart, Arshad Waheed, Patrick Schroeder, Helen Hu, John Hough and David Ocenosak |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

| **Key Risks** | **Probability** | **Impact** | **Status** |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
|  |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |