|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  |  | | **Project Status Report**  Initiative-158: Replace Silverlight  As of 6/28/2021 | **Project Manager:** Elizabeth White  **Project Sponsor:** Jeff Vail |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Initiative Number:** 158 | | **ETSC Priority:** N/A | | **Project Scheduled Completion Date:** 03/2022 | | | **Project Lifecycle:**  Execution | |
| **Project Description:** Replace Silverlight before end of life October 2021 | | | | | | | | |
| **Scope:** | **GREEN = No issues** | | **Schedule:** | | **GREEN = No issues** | **Resources:** | | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **End Date** | **Actual**  **Delivery Date** | **%**  **Complete** | **Actions/Comments** |
| Vendor Development Milestone #1 – Code Compiles | 01/04/2021 | 2/27/2021 | 4/20/2021 | 100% | Completed |
| Vendor Development Milestone #2 – Preview Release | 04/21/2021 | 5/29/2021 | 6/16/2021 | 100% | Completed |
| Vendor Development Milestone #3 – Alpha Release | 06/17/2021 | 7/24/2021 |  |  |  |
| Vendor Development Milestone #4 – Beta Release |  | 9/25/2021 |  |  |  |
| Vendor Development Milestone #5 – Release Candidate |  | 11/27/2021 |  |  |  |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** | |
| --- | --- | --- | --- |
| FN-212 | * Validated Vendor Development Milestone #2 – Preview Release, 6/28/2021. Task closed. | | * Validate Alpha Release Milestone #3 when it’s delivered by Userware |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| EDM Code Freeze | Jeff Barros | Approved | Decided – 12/21/2020 |
| IRS Form W-8BEN-E is the only form Userware needs to complete – a County of Sacramento Payee Data Record is not required for a foreign entity | Robert Salinas | N/A | Decided – 1/15/2021 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Risks** | **Probability** | **Impact** | **Status** |
| Userware development began 1/4/2021 prior to a PO being issued – PO was issued 2/23/2021 | Realized | High | Transfer Risk to Robert Salinas |
| Development Environment for OpenSilver not Ready by 1/4/21 | Not Realized | High | Development Environment Completed |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |