|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
|  |  |

 | **Project Status Report**Initiative-158: Replace SilverlightAs of 8/31/2021 | **Project Manager:** Elizabeth White**Project Sponsor:** Jeff Vail |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 158 | **ETSC Priority:** N/A | **Project Scheduled Completion Date:** 03/2022 | **Project Lifecycle:**  Execution |
| **Project Description:** Replace Silverlight before end of life October 2021 |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **GREEN = No issues** | **Resources:** | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **End Date** | **Actual****Delivery Date** | **%****Complete** | **Actions/Comments** |
| Vendor Development Milestone #1 – Code Compiles | 01/04/2021 | 2/27/2021 | 4/20/2021 | 100% | Completed |
| Vendor Development Milestone #2 – Preview Release | 04/21/2021 | 5/29/2021 | 6/16/2021 | 100% | Completed |
| Vendor Development Milestone #3 – Alpha Release | 06/17/2021 | ~~7/24/2021~~9/30/2021 |  |  |  |
| Vendor Development Milestone #4 – Beta Release | TBD | ~~9/25/2021~~10/29/2021 |  |  |  |
| Vendor Development Milestone #5 – Release Candidate | TBD | 11/27/2021 |  |  |  |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** |
| --- | --- | --- |
|  | * Met with Userware on 9/1 for regular status update:
	+ Delivery dates for Alpha and Beta releases have been pushed out again (see above).
* Userware reported that payment has not been received for the first two invoices that were submitted.
	+ Invoice #104089 dated 7/7 was processed on 8/10.
	+ Invoice #104078 dated 4/30 was not received by Fiscal for processing – they indicated they would process the invoice.
 | * Validate Alpha Release Milestone #3 when it’s delivered by Userware.
 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| EDM Code Freeze | Jeff Barros | Approved | Decided – 12/21/2020 |
| IRS Form W-8BEN-E is the only form Userware needs to complete – a County of Sacramento Payee Data Record is not required for a foreign entity | Robert Salinas | N/A | Decided – 1/15/2021 |

| **Key Risks** | **Probability** | **Impact** | **Status** |
| --- | --- | --- | --- |
| FileNet system is on extended support that expires 1/31/2022. IBM has agreed to extend support until 4/30/2022. Silverlight project should be completed by January 2022. | Not likely | Medium | Open |
| Userware Milestone Delivery – delivery of Milestones 1, 2, and 3 were late.  | Realized | Medium | Open |
| Userware development began 1/4/2021 prior to a PO being issued – PO was issued 2/23/2021 | Realized | High | Closed |
| Development Environment for OpenSilver not Ready by 1/4/21 | Not Realized | High | Closed |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |