|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
|  |  |

 | **Project Status Report**Initiative-158: Replace SilverlightAs of 02/03/2022 (Updated) | **Project Manager:** Elizabeth White**Project Sponsor:** Jeff Vail |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 158 | **ETSC Priority:** N/A | **Project Scheduled Completion Date:** 06/2022 | **Project Lifecycle:**  Execution |
| **Project Description:** Replace Silverlight before end of life October 2021 |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **Red = 3rd Date Change** | **Resources:** | **Yellow = New Developer & PM** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **End Date** | **Actual****Delivery Date** | **%****Complete** | **Actions/Comments** |
| Vendor Development Milestone #1 – Code Compiles | 01/04/2021 | 2/27/2021 | 4/20/2021 | 100% | Completed |
| Vendor Development Milestone #2 – Preview Release | 04/21/2021 | 5/29/2021 | 6/16/2021 | 100% | Completed |
| Vendor Development Milestone #3 – Alpha Release | 06/17/2021 | ~~7/24/2021~~9/30/2021 | 9/28/2021 | 100% | Completed |
| Vendor Development Milestone #4 – Beta Release | ~~10/1/2021~~11/22/2021 | ~~9/25/2021~~~~10/29/2021~~1/31/2022 | 2/1/2022 | 100% | Need to verify M4 |
| Vendor Development Milestone #5 – Release Candidate | 2/1/2022 | ~~11/27/2021~~~~3/11/2022~~4/11/2022 |  | 0% |  |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** |
| --- | --- | --- |
| FN-319 | * Milestone #4 – 30 functions to be developed:
	+ 26 requirements have been Closed
	+ 4 requirements are in Active state – 2 of the 4 requirements are not functional
		- Compile & Deploy Guide (received 2/3)
		- Replacing DevExpress Controls
	+ Pushed the 3 requirements in Active state to Milestone 5 delivery
* Informed on 1/3/2022 new project manager is taking over for Vasil, her name is Jayanthi Palanisamy.
 | * System Test Milestone #5 – Release Candidate when it’s delivered by Userware.
	+ Will be testing the EDM/OpenSilver code in the upgraded FileNet system.
 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| EDM Code Freeze | Jeff Barros | Approved | Decided – 12/21/2020 |
| IRS Form W-8BEN-E is the only form Userware needs to complete – a County of Sacramento Payee Data Record is not required for a foreign entity | Robert Salinas | N/A | Decided – 1/15/2021 |

| **Key Risks** | **Probability** | **Impact** | **Status** |
| --- | --- | --- | --- |
| #1. FileNet 5.2.1.6 system is on extended support that expires 1/31/2022. IBM has agreed to extend support until 4/30/2022. EDM/OpenSilver open-source code sits atop FileNet system. 02/03/2022 Update: OpenSilver Milestone #5 Release Candidate delivery date has changed to 4/11/2022. **Risk Mitigation Strategy:** EDM/OpenSilver was developed on FileNet 5.2.1.6 system. The FileNet 5.2.1.6 system will be upgraded and go into system test between April-June the plan is to system test the upgraded version of FileNet along with the EDM/OpenSilver code and remediate any issues found during the system test effort. | Realized | Unknown | Reopened |
| #5. There is a risk that the functionalities expected to be delivered by Userware vendor may not be completed with only one developer resource within the allotted timeframes. | Realized | Schedule | Open |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |