|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
|  |  |

 | **Project Status Report**Initiative-158: Replace SilverlightAs of 04/15/2022 | **Project Manager:** Elizabeth White**Project Sponsor:** Jeff Vail |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 158 | **ETSC Priority:** N/A | **Project Scheduled Completion Date:** 05/2022 | **Project Lifecycle:**  Execution |
| **Project Description:** Replace Silverlight before end of life October 2021 |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **Red = 3rd Date Change** | **Resources:** | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **End Date** | **Actual****Delivery Date** | **%****Complete** | **Actions/Comments** |
| Initiation | 12/09/2020 | 12/09/2020 | 12/09/2020 | 100% |  |
| Planning | 12/14/2020 | 09/30/2021 | 09/30/2021 | 100% |  |
| Execution | 01/04/2021 | 05/11/2022 |  |  |  |
| * Vendor Development Milestone #5 – Release Candidate
 | 2/1/2022 | ~~11/27/2021~~~~3/11/2022~~4/11/2022 | 4/11/2022 | 100% | Completed |
| * System Testing
 | 04/12/2022 | 04/26/2022 |  | 30% | In progress |
| * User Acceptance Testing
 | 04/27/2022 | 05/11/2022 |  |  |  |
| Closing | 05/23/2022 | 05/31/2022 |  |  |  |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** |
| --- | --- | --- |
| FN-214 | * Milestone #5 – all 19 functions have been delivered, task closed.
 | * Continue System Testing Milestone #5.
	+ Will be testing the EDM/OpenSilver code on FileNet Version 5.2.1.6.
 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| EDM Code Freeze | Jeff Barros | Approved | Decided – 12/21/2020 |
| IRS Form W-8BEN-E is the only form Userware needs to complete – a County of Sacramento Payee Data Record is not required for a foreign entity | Robert Salinas | N/A | Decided – 1/15/2021 |

| **Key Risks** | **Probability** | **Impact** | **Status** |
| --- | --- | --- | --- |
| #1. FileNet 5.2.1.6 system is on extended support that expires 1/31/2022. IBM has agreed to extend support until 4/30/2022. EDM/OpenSilver open-source code sits atop FileNet system. 02/03/2022 Update: OpenSilver Milestone #5 Release Candidate delivery date has changed to 4/11/2022. **Risk Mitigation Strategy:** EDM/OpenSilver is developed on FileNet 5.2.1.6 system (before FileNet upgrade). If Userware delivers M5 on 4/11/2022 as planned, the plan is to system test the FileNet 5.2.1.6 system with the EDM/OpenSilver code. The FileNet 5.2.1.6 system will be upgraded and goes into system test in July as planned.  | Realized | Unknown | Closed |
| #5. There is a risk that the functionalities expected to be delivered by Userware vendor may not be completed with only one developer resource within the allotted timeframes. | Realized | Schedule | Closed |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |