|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| For the  |  |

 | **Project Status Report**Initiative-158: Replace SilverlightAs of 06/06/2022 | **Project Manager:** Elizabeth White**Project Sponsor:** Jeff Vail |

|  |  |  |  |
| --- | --- | --- | --- |
| **Initiative Number:** 158 | **ETSC Priority:** N/A | **Project Target Completion Date:** 06/2022 | **Project Lifecycle:**  Execution |
| **Project Description:** Replace Silverlight before end of life October 2021 |
| **Scope:** | **GREEN = No issues** | **Schedule:** | **Red = 3rd Date Change** | **Resources:** | **GREEN = No issues** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestones** | **Start Date** | **End Date** | **Actual****Delivery Date** | **%****Complete** | **Actions/Comments** |
| Initiation | 12/09/2020 | 12/09/2020 | 12/09/2020 | 100% |  |
| Planning | 12/14/2020 | 09/30/2021 | 09/30/2021 | 100% |  |
| Execution | 01/04/2021 | 05/23/2022 |  | 83% |  |
| * System Testing
 | 04/12/2022 | ~~04/29/2022~~05/06/2022 | 05/17/2022 | 100% |  |
| * User Acceptance Testing
 | ~~05/02/2022~~~~05/09/2022~~05/17/2022 | ~~05/20/2022~~05/31/2022 | 05/31/2022 | 100% | Obtained formal customer sign-off. |
| * Implementation
 | 05/31/2022 | 06/30/2022 |  | 14% | EDM/OpenSilver Production Rollout scheduled for Saturday, 6/18/2022 |
| Closing | 05/31/2022 | 06/30/2022 |  |  |  |

| **IT Task #** | **Completed Tasks This Reporting Period** | **Planned Activities for Next Reporting Period** |
| --- | --- | --- |
| FN-224FN-238FN-215FN-237FN-226 | Formally close out system test, remediated INIT158-26Completed UAT coordination with customers, task closed.Completed UAT testing, task closed.Communication Plan included with Cutover, task closed.Obtained formal acceptance of OpenSilver software, task closed. | * Continue development of Cutover Plan
* Rollout EDM/OpenSilver to Production
* Start post-implementation activities
* Start compiling the closing report
 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Decisions** | **Decided by** | **Outcome** | **Status** |
| EDM Code Freeze | Jeff Barros | Approved | Decided – 12/21/2020 |
| IRS Form W-8BEN-E is the only form Userware needs to complete – a County of Sacramento Payee Data Record is not required for a foreign entity | Robert Salinas | N/A | Decided – 1/15/2021 |

| **Key Risks** | **Probability** | **Impact** | **Status** |
| --- | --- | --- | --- |
| No Key Risks to Report |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Issues** | **Impact** | **Priority** | **Status** |
| No Key Issues to Report |  |  |  |