## BatchDef
Round 1 | Development Websites that seem easy to send over
RegionalWebsites tiis01
Round 2 | QA websites that seem easy to send over
Round 3 | Production websites that seem easy to send over
Round 4 | Application servers: WIMS, Maximo, Maximo, LIMS, Meridian
The process | [14 empty] | Batch 1 | batch 2
1 | Select a batch of websites
[12 empty] | Gather a group of websites |  |  | Development websites at RegSan | Development websites at sasd
[12 empty] | submit list to testers |  |  | 2019-06-04 | 2019-06-20
2 | Test these websites to make sure they are currently working | [10 empty] | Finalize the list
|  | if it's a sharepoint website - remove it from the list (check batches 2 and 3 also) | [9 empty] | send list to Tracey Jira
|  | If the site doesn't work, have it fixed before sending the batch to conversion | [10 empty] | coordinate a date for website conversion
|  | send messages to affected users of pending changes. | [10 empty] | mark coordindate/confirm testing schedule
tracey will get conversion done
3 | Send the batch of websites for conversion to https
Change control. 1 per server or batch, or dtech request
test website agin
Mark alert people to test
4 | test the websites
|  | Check inter website relationships | [9 empty] | Repeat and lessons learned review
Note any issues, for consideration for the next batch
|  |  |  | 2019-10-21 |  | 2019-09-24 |  | 2019-09-11 |  | 2019-08-20
Phases of conversion |  |  | total records | 236 | % | 243 | % | 244 | % | 284 | % |  |  | %
1 | website has been selected for conversion to https |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | #DIV/0!
2 | programmers do pretesting of website |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | #DIV/0!
7 | Website request submitted to convert this to https |  |  | 6 | 2.542% | 8 | 3.292% |  | 0% |  | 0% |  |  | #DIV/0!
3 | Tracey has the websites converted |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | #DIV/0!
4 | mark/shabab tests websites that have been converted |  |  | 32 | 13.56% | 35 | 14.4% | 35 | 14.34% | 48 | 16.9% |  |  | #DIV/0!
5 | programmers test websites that have been converted. |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | #DIV/0!
6 | website has been converted successfully to https |  |  | 10 | 4.237% | 11 | 4.527% | 11 | 4.508% | 1 | 0.3521% |  |  | #DIV/0!
|  |  | no status |  | 0% |  | 0% | 197 | 80.74% | 197 | 69.37% |  |  | #DIV/0!

## Servers
A nieve list of servers hosting websites
SASD
| sasddiis1 | Development
| sasdpiis1 | Production
Regional
| RSD-TIIS01 | Development
| RSQ-IIS01 | QA
| SDAD-MERIDIAN | Development
| RSP-IIS01 | Production
Reporting Servers
MPSRSL01
sasdDdb1
sasdPdb1
SDAD-SRS01
Lims
RSDLIMSAPP01
RSPLIMSAPP01
Maximo
SADDMXAPP1
SADDMXAPP2

## Batch
OrgOrder | Source | Owner | Batch | Env | Application Name | Type | Server | Link | Framework Version | Comment (8/29/2019 test - just boot status) | BeforeHTTP Conversion | Notes | Conversion Status | After HTTPS Conversion - preliminary check | Notes for Q conversion | After conversion Website Address | Conversion notes
16 | Shabab | Regional |  | Prod | Absence Request | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/tsSRWTP/default.asp?Source=SRWTP |  | 8/29/2019 - ok
253 | Pedro | Regional |  | Dev | AMDDDev |  | RSD-TIIS01
68 | Tracey | Sasd |  | Dev | Attendance | Custom | sasddiis1 | http *:80:sasdattendancedev.cospub.saccounty.net, http *:80:sasdattendancedev | ASP | 8/29/2019 - 404
38 | Tracey | Sasd |  | Prod | Attendance | Custom | sasdpiis1 | http *:80:sasdattendance, http *:80:sasdattendance.cospub.saccounty.net |  | 8/29/2019 - 500
440 | Mark | Sasd |  | Prod | Attendance Tracking | Custom | sasdpiis1 | http://sasdattendance/walDataEntry.asp |  | 8/29/2019 - 500
418 | Mark | Regional |  | Prod | Attendance Tracking | SSRS |  | http://mpsrsl01/Reports/Pages/Folder.aspx?ItemPath=%2fAbsence+Log |  | 8/29/2019 - ok
442 | Mark | Sasd | 2 | Dev | Business Analyst Website | Custom | sasddiis1 | https://sasdbadev.saccounty.net/ |  | 8/29/2019 - ok | 1=Works - My Map. In Chrome I need to log in, and it displays a GIS map from 'OpenStreetMap' |  | 6 - website converted successfully to https | SasdApps-7 - 8/20 - https://sasdbadev.cospub.saccounty.net/ - Cant Reach this page8/12 - https://sasdbadev.saccounty.net/ - 504 - service is unavailable. |  | https://sasdbadev.saccounty.net/
443 | Mark | Sasd | 2 | Dev | Business Analyst Website | Custom | sasddiis1 | http://sasdbadev/ |  | 8/29/2019 - ok | 1 - 6/20 - sent message to Mike, Don - itsec-547 |  | 6 - website converted successfully to https | 8/12 - not a valid site - use .saccounty.net |  | https://sasdbadev.saccounty.net/
|  | Regional | 1 | Dev | Children Site Example: PRS | Custom |  | http://regionalsandev.saccounty.net/requests/default.asp |  | 8/29/2019 - ok |  |  | 4 - Shabab tests websites that have been converted | 7/25/2019 - maw - works |  | https://regionalsandev.saccounty.net/requests/default.asp
445 | Mark | Sasd | 2 | Dev | Clerical | Custom | sasddiis1 | http://sasdclericaldev/ | 4.6.1 | 8/29/2019 - ok | 2=Works. (In IE and in Chrome - but you do have to log in) |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-6, sasdapps-19 |  | https://sasdclericaldev.saccounty.net/
39 | Tracey | Sasd |  | Prod | Clerical | Custom | sasdpiis1 | http *:80:sasdclerical, http *:80:sasdclerical.cospub.saccounty.net | 4.6.1 | 8/29/2019 - ok
444 | Mark | Sasd |  | Prod | Clerical | Custom | sasdpiis1 | http://sasdclerical/ | 4.6.1 | 8/29/2019 - ok
71 | Tracey | Sasd |  | QA | Clerical | Custom | sasddiis1 | http *:80:sasdclericaltest, http *:80:sasdclericaltest.cospub.saccounty.net | 4.6.1 | 8/29/2019 - ok - history issue
446 | Mark | Sasd |  | QA | Clerical | Custom | sasddiis1 | http://sasdclericaltest/ | 4.6.1 | 8/29/2019 - ok - history issue
72 | Tracey | Sasd | 2 | Dev | CMMS Sewer | Custom | sasddiis1 | http *:80:sasdcmmssewerdev, http *:80:sasdcmmssewerdev.cospub.saccounty.net | ASP mix with ASP.Net 1.0 | 8/29/2019 - ASP - NT Authority error |  |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-5, sasdapps-19 |  | https://sasdcmmssewerdev.saccounty.net/login.asp
40 | Tracey | Sasd |  | Prod | CMMS Sewer | Custom | sasdpiis1 | http *:80:sasdcmmssewer, http *:80:sasdcmmssewer.cospub.saccounty.net |  | 9/3/2019 - works
447 | Mark | Sasd |  | Prod | CMMS Sewer | Custom | sasdpiis1 | http://sasdcmmssewer/portal.asp |  | 9/3/2019 - works
513 | Mark | Sasd |  | Dev | Customer Surveys | Custom | sasddiis1 | http://sasdsurveydev/ |  | 8/29/2019 - Cannot open database "SURVEY" requested by the login. The login failed. Login failed for user 'COSPUB\sasdsurveydev'. | The server principal "COSPUB\sasdsurveydev" is not able to access the database "Staff" under the current security context. | IT Sec - 553 - New
74 | Tracey | Sasd |  | Dev | Data Dictionary | Custom | sasddiis1 | http *:80:sasddddev, http *:80:sasddddev.cospub.saccounty.net |  | 8/29/2019 - Cant reach this page - ITOPS-357
452 | Mark | Sasd |  | Dev | Data Dictionary | Custom | sasddiis1 | http://sasddddev |  | 8/29/2019 - Cant reach this page - ITOPS-357 | Cant reach this page' | Skip - website down
42 | Tracey | Sasd |  | Prod | Data Dictionary | Custom | sasdpiis1 | http *:80:sasddd, http *:80:sasddd.cospub.saccounty.net |  | 8/29/2019 - ok
449 | Mark | Sasd |  | Prod | Data Dictionary | Custom | sasdpiis1 | http://sasddd |  | 8/29/2019 - ok
125 | Tracey | Regional |  | Dev | Default FTP Site | Custom | RSD-TIIS01 | *:21
147 | Tracey | Regional |  | Prod | Default FTP Site | OOB | RSP-IIS01 | *:21 |  |  | Meridian
138 | Tracey | Regional |  | QA | Default FTP Site | OOB | RSQ-IIS01
205 | Pedro | Sasd |  | Dev | Default Web Site | Custom | sasddiis1
37 | Tracey | Sasd |  | Prod | Default Web Site | Custom | sasdpiis1 | http *:80:, net.pipe *, net.tcp 808:*, net.msmq localhost, msmq.formatname localhost
148 | Tracey | Regional |  | Prod | Default Web Site | OOB | RSP-IIS01 | *:80 |  |  | Meridian
139 | Tracey | Regional |  | QA | Default Web Site | OOB | RSQ-IIS01 |  |  | sasd production website
206 | Pedro | Sasd |  | Dev | DefaultAppPool | Custom | sasddiis1
169 | Pedro | Sasd |  | Prod | DefaultAppPool | Custom | sasdpiis1
465 | Mark | Sasd | 2 | Dev | Doc Record Tracking | Custom | sasddiis1 | http://sasddocumentationdev/SearchForm.aspx |  | 9/3/2019 - works - https://sasddocumentationdev.saccounty.net/NewForm.aspx | 2 | Adjusted cospub\sasddocdev, added to staff with db_data reader permission. | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-19 |  | https://sasddocumentationdev.saccounty.net/NewForm.aspx
464 | Mark | Sasd |  | Prod | Doc Record Tracking | Custom | sasdpiis1 | http://sasddocumentation/SearchForm.aspx |  | 8/29/2019 - 500 - itops-358 | [5 empty] | https://sasdebookdev.saccounty.net/ | cospub\sasdebookdev, needed to be added as a user to the eBook database in dev
17 | Shabab | Regional |  | Prod | Document Change (DCN) | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/dcn/Choose.asp |  | 8/29/2019 - ok | [5 empty] | https://sasdemployeedev.saccounty.net/
43 | Tracey | Sasd |  | Prod | Documentation | Custom | sasdpiis1 | http *:80:sasddocumentation, http *:80:sasddocumentation.cospub.saccounty.net |  | 8/29/2019 - 500 - itops-358
76 | Tracey | Sasd | 2 | Dev | Resource Book | Custom | sasddiis1 | http *:80:sasdebookdev, http *:80:sasdebookdev.cospub.saccounty.net |  | 8/29/2019 - 503 - itops-359 | Lou - Works in IE; Not in Chrome |  | 4 - Mark tests websites that have been converted
44 | Tracey | Sasd |  | Prod | Resource Book | Custom | sasdpiis1 | http *:80:sasdebook, http *:80:sasdebook.cospub.saccounty.net |  | 9/3/2019 - works
18 | Shabab | Regional |  | Prod | EDM | Custom | RSP-FNAE01/02 | http://edm.srcsd.saccounty.net/ |  | 8/29/2019 - OK
77 | Tracey | Sasd | 2 | Dev | Employee Maintenance | Custom | sasddiis1 | http *:80:sasdemployeedev, http *:80:sasdemployeedev.cospub.saccounty.net | 4.6.1 | 8/29/2019 - ok | Both ASP and ASP.Net pages work |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-19, sasdapps-3 |  | https://sasdemployeedev.saccounty.net/
45 | Tracey | Sasd |  | Prod | Employee Maintenance | Custom | sasdpiis1 | http *:80:sasdemployee, http *:80:sasdemployee.cospub.saccounty.net | 4.6.1 | 8/29/2019 - ok
468 | Mark | Sasd |  | Prod | Employee Maintenance | Custom | sasdpiis1 | http://sasdemployee/ | 4.6.1 | 8/29/2019 - ok | [5 empty] | https://sasdplansdev.saccounty.net/ | Removed Short Name
78 | Tracey | Sasd |  | QA | Employee Maintenance | Custom | sasddiis1 | http *:80:sasdemployeetest, http *:80:sasdemployeetest.cospub.saccounty.net | 4.6.1 | 8/30/2019 - 401 - stuck at login window. ITOPS-362
471 | Mark | Sasd |  | QA | Employee Maintenance | Custom | sasddiis1 | http://sasdemployeetest/ | 4.6.1 | 8/30/2019 - 401 - stuck at login window. ITOPS-362
128 | Tracey | Regional | 1 | Dev | FileUpSampleSite | Custom | RSD-TIIS01 | :59319 |  | Not configured. |  | from Tracey 7/15/2019: • What URL do you want to use for FileUpSampleSite? We cannot use the serverhostname:59319. Please work with either your staff or the customer that uses the site to come up with a unique URL. 7/16/2019 - This site is not in use. This was excluded from the conversion. | 4 - Shabab tests websites that have been converted | 7/25 - maw - I get a 'Can't reach this page' message
149 | Tracey | Regional |  | Prod | FileUpSampleSite | OOB | RSP-IIS01 | :59319
140 | Tracey | Regional |  | QA | FileUpSampleSite | Custom | RSQ-IIS01 |  |  | SASD Development Website
251 | Pedro | Regional |  | Dev | FileUpSamplesSite | OOB | RSD-TIIS01
286 | Pedro | Regional |  | Prod | FileUpSamplesSite |  | rsp-iis01
19 | Shabab | Regional |  | Prod | Fiscal Budget Application | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/budget/ |  | 8/30/2019 - ok
507 | Mark | Sasd | 2 | Dev | Grower Address Summary | Custom | sasddiis1 | https://sasdscapodev.saccounty.net/ |  | 8/30/2019 - ok | works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-23 |  | https://sasdscapodev.saccounty.net/
505 | Mark | Sasd |  | Prod | Grower Address Summary | Custom | sasdpiis1 | http://sasdscapo |  | 8/30/2019 - 403
506 | Mark | Sasd |  | Prod | Grower Address Summary | Custom | sasdpiis1 | http://sasdscapo.cospub.saccounty.net |  | 8/30/2019 - 403
508 | Mark | Sasd |  | QA | Grower Address Summary | Custom | sasddiis1 | http://sasdscapotest |  | 8/30/2019 - ok
509 | Mark | Sasd |  | QA | Grower Address Summary | Custom | sasddiis1 | http://sasdscapotest.cospub.saccounty.net |  | 8/30/2019 - ok
282 | Pedro | Regional |  |  | honeyguide |  |  | ?? |  | tfs 2019 installed at plant
257 | Pedro | Regional |  | Dev | HORIZON12 |  | LIMSDEV02
273 | Pedro | Regional |  | QA | HORIZON12 | Vended | rsqlimsapp01
258 | Pedro | Regional |  | Dev | HorizonApi |  | LIMSDEV02
274 | Pedro | Regional |  | QA | HorizonApi | Vended | rsqlimsapp01
259 | Pedro | Regional |  | Dev | HorizonApi_External |  | LIMSDEV02
287 | Pedro | Regional |  | Prod | idea |  | rsp-iis01
150 | Tracey | Regional |  | prod | idea.regionalsan.saccounty.net | Custom | RSP-IIS01 | idea.regionalsan.saccounty.net |  | 8/30/2019 - ok
126 | Tracey | Regional | 1 | Dev | ideadev2012.srcsd.saccounty.net | Custom | RSD-TIIS01 | ideadev2012.srcsd.saccounty.net |  | 8/30/2019 - iis default page |  | from Tracey 7/12/2019: • Does Ideadev2012.saccounty.net instead of Ideadev2012.srcsd.saccounty.net work? We do not have a * cert for srcsd.saccounty.net, only *.saccounty.net. From Shabab 7/12 - I don’t see any issue with IDEA change, however Akhil may confirm. | 4 - Shabab tests websites that have been converted | 7/25/2019 - maw - boots
269 | Pedro | Regional |  | QA | ideaqa2012 |  | rsq-iis01 |  |  | 8/30/2019 - iis default page
79 | Tracey | Sasd | 2 | Dev | IT Support Inventory Mgmt | Custom | sasddiis1 | http *:80:sasdinventorydev, http *:80:sasdinventorydev.cospub.saccounty.net |  | 8/30/2019 - ok | Lou - Works in IE; Not in Chrome |  | 4 - Mark tests websites that have been converted |  |  | https://sasdinventorydev.saccounty.net/
474 | Mark | Sasd | 2 | Dev | IT Support Inventory Mgmt | Custom | sasddiis1 | http://sasdinventorydev/AssignedInventory.aspx |  | 8/30/2019 - ok | 2 = This was working until I went to Chrome - then I got a Login Failed for NT Authority \ Anonymous Logon |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-19 - seems to be readonly. |  | https://sasdinventorydev.saccounty.net/
46 | Tracey | Sasd |  | Prod | IT Support Inventory Mgmt | Custom | sasdpiis1 | http *:80:sasdinventory, http *:80:sasdinventory.cospub.saccounty.net |  | 8/30/2019 - ok
473 | Mark | Sasd |  | Prod | IT Support Inventory Mgmt | Custom | sasdpiis1 | http://sasdinventory/AssignedInventory.aspx |  | 8/30/2019 - ok
294 | Pedro | Regional |  | Prod | Keystone |  | rsp-iis01
129 | Tracey | Regional | 1 | Dev | KeystoneDev | Custom | RSD-TIIS01 | *:8080, keystonedev.saccounty.net:8080, rskeydev.saccounty.net:8080 |  | 8/30/2019 - ok - brings me to a login page |  |  | 4 - Shabab tests websites that have been converted | 7/25/2019 - maw - gives a message - this site is not secure |  | https://keystonedev.saccounty.net/
20 | Shabab | Regional |  | Prod | LIMS | Vended | RSPLIMSAPP01 | http://rsplimsapp01.cospub.saccounty.net |  | 8/30/2019 - ok - brings me to a login page |  | Horizon
256 | Pedro | Regional |  | Dev | LIMSDEV02 |  | LIMSDEV02
476 | Mark | Sasd | 2 | Dev | Lobby Player | Custom | sasddiis1 | http://sasdlobbypcdev/ | 4.6.1 | 8/30/2019 - ok | Works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-19 |  | https://sasdlobbypcdev.saccounty.net/
47 | Tracey | Sasd |  | Prod | Lobby Player | Custom | sasdpiis1 | http *:80:sasdlobbypc, http *:80:sasdlobbypc.cospub.saccounty.net | 4.6.1 | 8/30/2019 - ok
475 | Mark | Sasd |  | Prod | Lobby Player | Custom | sasdpiis1 | http://sasdlobbypc/ | 4.6.1 | 8/30/2019 - ok
80 | Tracey | Sasd |  | QA | Lobby Player | Custom | sasddiis1 | http *:80:sasdlobbypcdev, http *:80:sasdlobbypcdev.cospub.saccounty.net | 4.6.1 | 8/30/2019 - ok
81 | Tracey | Sasd |  | Dev | Lou | Custom | sasddiis1 | http *:80:sasdloudev, http *:80:sasdloadev.cospub.saccounty.net |  | 8/30/2019 - ok
512 | Mark | Sasd |  | Prod | Mail Generator for Surveys | Custom | sasdpiis1 | http://sasdsurvey/ |  | 8/30/2019 - ok
82 | Tracey | Sasd |  | QA | Max2GenQa | Custom | sasddiis1 | http *:80:sasdmax2gnetqa, http *:80:sasdmax2gnetqa.cospub.saccounty.net |  | 8/30/2019 - ok
83 | Tracey | Sasd | 2 | Dev | Max2gnet | Custom | sasddiis1 | http *:80:sasdmax2gnetdev, http *:80:sasdmax2gnetdev.cospub.saccounty.net |  | 8/30/2019 - ok |  |  | 4 - Mark tests websites that have been converted |  |  | https://sasdmax2gnetdev.saccounty.net/
48 | Tracey | Sasd |  | Prod | Max2gnet | Custom | sasdpiis1 | http *:80:sasdmax2gnet, http *:80:sasdmax2gnet.cospub.saccounty.net |  | 8/30/2019 - ok
152 | Tracey | Regional |  | Dev | MAXDEV | Vended | RSD-TIIS01 | http://srcsdd-maximo04/maximo/webclient/login/login.jsp |  | 10/29/2019 - ok |  | maxr-180 | 7 - submitted request for conversion
289 | Pedro | Regional |  | Dev | MAXDEV | Dev | rsp-iis01
93 | Tracey | Sasd | sasdapps-43 | Dev | Maximo | Custom | sasddiis1 | http *:80:sasdmxdev | Java | 8/30/2019 - ok |  | redirects to sasd maximo dev | 7 - submitted request for conversion
96 | Tracey | Sasd |  | Dev | Maximo | Custom | sasddiis1 | http *:80:sasdmxtrain |  | 8/30/2019 - webpage cannot be found
97 | Tracey | Sasd |  | Dev | Maximo | Custom | sasddiis1 | http *:80:sasdmxvm |  | 8/30/2019 - no results for sasdmxvm/
456 | Mark | Sasd | sasdapps-43 | Dev | Maximo | Vended |  | http://sasddmxapp1/maximo | Java | 8/30/2019 - ok |  |  | 7 - submitted request for conversion
457 | Mark | Sasd | sasdapps-43 | Dev | Maximo | Vended |  | http://sasddmxapp1:81/maximo | Java | 8/30/2019 - ok |  |  | 7 - submitted request for conversion
459 | Mark | Sasd | sasdapps-43 | Dev | Maximo | Vended |  | http://sasddmxapp1:9090/maximo | Java | 8/30/2019 - ok |  |  | 7 - submitted request for conversion
461 | Mark | Sasd |  | Dev | Maximo | Vended |  | http://sasddmxapp2/maximo/ui/login |  | 8/30/2019 - ok |  | maximo testing
462 | Mark | Sasd |  | Dev | Maximo | Vended |  | http://sasddmxapp2:9083/meaweb/os/mxasset |  | 8/30/2019 - ok |  | serelet running
463 | Mark | Sasd |  | Dev | Maximo | Vended |  | http://sasddmxapp2:9083/meaweb/wsdl/MXASSET.wsdl |  | 8/30/2019 - this page cannot be found
548 | Mark | Regional |  | Dev | Maximo | Vended |  | http://srcsdd-cognos04.cospub.saccounty.net/ibmcognos/cgi-bin/cognos.cgi |  | 8/30/2019 - ok
549 | Mark | Regional |  | Dev | Maximo | Vended |  | http://srcsdd-maximo04/maximo/webclient/login/login.jsp |  | 8/30/2019 - ok
21 | Shabab | Regional |  | prod | Maximo | Vended | SRCSDP-MAXIMO04 | http://srcsdp-maximo04.cospub.saccounty.net/maximo/ui/ |  | 8/20/2019 - ok
54 | Tracey | Sasd |  | Prod | Maximo | Custom | sasdpiis1 | http *:80:sasdmxprod |  | 8/30/2019 - ok
153 | Tracey | Regional |  | prod | MAXIMO | Vended | RSP-IIS01 | maximo.saccounty.net, maximo |  | 8/30/2019 - ok |  | regional maximo
478 | Mark | Sasd |  | Prod | Maximo | Custom | sasdpiis1 | http://sasdmaximoutilities/display.aspx |  | 8/30/2019 - ok
494 | Mark | Sasd |  | Prod | Maximo | Vended | sasdpdb1 | http://sasdpdb1/reports |  | 8/30/2019 - ok
503 | Mark | Sasd |  | Prod | Maximo | Vended |  | http://sasdpmxapp2:9085 |  | 8/30/2019 - this webpage cannot be found | Meridian
547 | Mark | Regional |  | prod | Maximo | Vended |  | http://srcsdb-maximo04/maximo |  | 8/30/2019 - ok
94 | Tracey | Sasd |  | Qa | Maximo | Custom | sasddiis1 | http *:80:sasdmxqa |  | 8/30/2019 - ok
490 | Mark | Sasd |  | Qa | Maximo | Vended | sasddiis1 | http://sasdmxqa/ |  | 8/30/2019 - ok
95 | Tracey | Sasd |  | SB | Maximo | Custom | sasddiis1 | http *:80:sasdmxsb |  | 8/30/2019 - ok
491 | Mark | Sasd |  | Train | Maximo | Vended | sasddiis1 | http://sasdmxtrain |  | 8/30/2019 - this webpage cannot be found
546 | Mark | Regional |  |  | Maximo | Vended |  | http://srcsdb-maximo04.cospub.saccounty.net/maximo-x/ |  | 8/30/2019 - this webpage cannot be found
|  | sasd | sasdapps-43 | dev | Maximo | Vended |  | http://sasdmxdev | Java | 8/30/2019 - ok |  |  | 7 - submitted request for conversion
141 | Tracey | Regional |  | QA | Maximo Regional | Vended | RSQ-IIS01
154 | Tracey | Regional |  | QA | Maximo Regional | Vended | RSP-IIS01 | maxqa.saccounty.net, maxqa |  | 8/30/2019 - ok
270 | Pedro | Regional |  | QA | Maximo Regional |  | rsq-iis01
290 | Pedro | Regional |  | Qa | Maximo Regional | QA | rsp-iis01
450 | Mark | Sasd |  | Dev | Maximo Reports | Custom | sasdddb1 | http://sasdddb1/Reports/Pages/Folder.aspx?ItemPath=%2fMaximo&ViewMode=List |  | 8/30/2019 - ok - but folder missing
460 | Mark | Sasd |  | Dev | Maximo Testing | Vended |  | http://sasddmxapp2/maximo |  | 8/30/2019 - ok
84 | Tracey | Sasd | 2 | Dev | Maximo Utilities | Custom | sasddiis1 | http *:80:sasdmaxutilsdev, http *:80:sasdmaxutilsdev.cospub.saccounty.net | 4 | 8/30/2019 - ok |  |  | 4 - Mark tests websites that have been converted |  |  | https://sasdmaxutilsdev.saccounty.net/
480 | Mark | Sasd | 2 | Dev | Maximo Utilities | Custom | sasddiis1 | http://sasdmaxutilsdev/display.aspx | 4 | 8/30/2019 - ok | Works | Maximo Utilties ssrs 2 maxutils 2 maximo | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-13, sasdapps-19 |  | https://sasdmaxutilsdev.saccounty.net/
49 | Tracey | Sasd |  | Prod | Maximo Utilities | Custom | sasdpiis1 | http *:80:sasdmaximoutilities, http *:80:sasdmaximoutilities.cospub.saccounty.net |  | 8/30/2019 - ok
85 | Tracey | Sasd |  | QA | Maximo Utilities | Custom | sasddiis1 | http *:80:sasdmaxutilsqa, http *:80:sasdmaxutilsqa.cospub.saccounty.net | 4 | 8/30/2019 - ok
481 | Mark | Sasd |  | QA | Maximo Utilities | Custom | sasddiis1 | http://sasdmaxutilsqa/display.aspx | 4 | 8/30/2019 - ok
86 | Tracey | Sasd |  | SB | Maximo Utilities | Custom | sasddiis1 | http *:80:sasdmaxutilssb, http *:80:sasdmaxutilssb.cospub.saccounty.net | 4 | 8/30/2019 - ok
482 | Mark | Sasd |  | SB | Maximo Utilities | Custom | sasddiis1 | http://sasdmaxutilssb/ | 4 | 8/3/2019 - ok (but it says Development)
87 | Tracey | Sasd |  | Dev | MCAP | Custom | sasddiis1 | http *:80:sasdmcapdev, http *:80:sasdmcapdev.cospub.saccounty.net | 4 | 8/30/2019 - Configuration error. *** Need to create ticket - or solve myself
484 | Mark | Sasd |  | Dev | MCAP | Custom | sasddiis1 | http://sasdmcapdev/ | 4 | 8/30/2019 - Configuration error. *** Need to create ticket - or solve myself | Throws a Configuration Error from the Entity Framework | ITSEC-555
50 | Tracey | Sasd |  | Prod | MCAP | Custom | sasdpiis1 | http *:80:sasdmcap, http *:80:sasdmcap.cospub.saccounty.net | 4 | 8/30/2019 - works
483 | Mark | Sasd |  | Prod | MCAP | Custom | sasdpiis1 | http://sasdmcap/ | 4 | 8/30/2019 - works
88 | Tracey | Sasd |  | Qa | MCAP | Custom | sasddiis1 | http *:80:sasdMCAPTestdev, http *:80:sasdMCAPTestdev.cospub.saccounty.net | 4 | 8/30/2019 - 500 internal server error **** Need to create ticket
119 | Tracey | Sasd |  | Qa | Metrics | Custom | sasddiis1 | http *:80:SasdMetricsTest.cospub.saccounty.net, http *:80:SasdMetricsTest |  | 9/3/2019 - Web.config error - http://sasdmetricstest.saccounty.net/
89 | Tracey | Sasd | 2 | Dev | Midnight | Custom | sasddiis1 | http *:80:sasdmidnightdev, http *:80:sasdmidnightdev.cospub.saccounty.net |  | 9/3/2019 - works |  |  | 4 - Mark tests websites that have been converted |  |  | https://sasdmidnightdev.saccounty.net/search.aspx
51 | Tracey | Sasd |  | Prod | Midnight | Custom | sasdpiis1 | http *:80:sasdmidnight, http *:80:sasdmidnight.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdmidnight/
486 | Mark | Sasd |  | Prod | Midnight | Custom | sasdpiis1 | http://sasdmidnight/default.aspx |  | 9/3/2019 - Source cannot be found
90 | Tracey | Sasd | 2 | Dev | New Hire | Custom | sasddiis1 | http *:80:sasdnewhiredev, http *:80:sasdnewhiredev.cospub.saccounty.net |  | 9/3/2019 - works - https://sasdnewhiredev.saccounty.net/new.aspx | Lou - Works in IE; Not in Chrome |  | 4 - Mark tests websites that have been converted |  |  | https://sasdnewhiredev.saccounty.net/new.aspx
52 | Tracey | Sasd |  | Prod | NewHire | Custom | sasdpiis1 | http *:80:sasdnewhire, http *:80:sasdnewhire.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdnewhire/new.aspx
91 | Tracey | Sasd | 2 | Dev | Plans | Custom | sasddiis1 | http *:80:sasdplansdev, http *:80:sasdplansdev.cospub.saccounty.net |  | 9/3/2019 - works - https://sasdplansdev.saccounty.net/ | Works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-22
53 | Tracey | Sasd |  | Prod | Plans | Custom | sasdpiis1 | http *:80:sasdplans, http *:80:sasdplans.cospub.saccounty.net |  | 9/3/2019 - works http://sasdplans/Construction.aspx
500 | Mark | Sasd |  | Prod | Plans | Custom | sasdpiis1 | http://sasdplans/home.aspx |  | 9/3/2019 - works http://sasdplans/Construction.aspx
92 | Tracey | Sasd |  | QA | Plans | Custom | sasddiis1 | http *:80:sasdplanstestdev, http *:80:sasdplanstestdev.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdplanstestdev/
502 | Mark | Sasd |  | QA | Plans | Custom | sasddiis1 | http://sasdplanstestdev/home.aspx |  | 9/3/2019 - works - http://sasdplanstestdev/
283 | Pedro | Regional |  |  | PMO
22 | Shabab | Regional |  | Prod | PMR | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/pmr |  | 9/3/2019 - works
26 | Shabab | Regional |  | Prod | PRS | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/Requests/default.asp |  | 9/3/2019 - works
24 | Shabab | Regional |  | Prod | RCTS | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/rcts |  | 9/3/2019 - works
23 | Shabab | Regional |  | Prod | Records Mgmt. Off-site Storage | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/offsitestorage/ |  | 9/3/2019 - works
155 | Tracey | Regional |  | Prod | regionalsan.saccounty.net | Custom | RSP-IIS01 | regionalsan.saccounty.net |  | 9/3/2019 - 403.14 error - ** Talk to Shabab
250 | Pedro | Regional | 1 | Dev | regionalsandev | OOB | RSD-TIIS01 | http://regionalsandev/ |  | 9/3/2019 - 403 - https://regionalsandev.saccounty.net/ - *** Talk to Shabab |  |  | 4 - Shabab tests websites that have been converted | 7/25/2019 - maw - I get a 'this site is not secure'
127 | Tracey | Regional | 1 | Dev | regionalsandev.saccounty.net | Custom | RSD-TIIS01 | regionalsandev.saccounty.net |  | 9/3/2019 - 403.14 error - ** Talk to Shabab |  | Regional San base Site. All other websites (prs, pmr etc. are under this site) | 4 - Shabab tests websites that have been converted | 7/25 - maw - I get 403 - forbidden: Access is denied.
142 | Tracey | Regional |  | QA | regionalsanqa.saccounty.net | Custom | RSQ-IIS01 | regionalsanqa.saccounty.net |  | 9/3/2019 - 403.14 - ** Talk to Shabab
435 | Mark | Regional | 1 | Dev | RegSan | Custom | RSD-TIIS01 | http://regionalsandev.saccounty.net/ |  | 9/3/2019 - 403.14 error - ** Talk to Shabab |  |  | 4 - Shabab tests websites that have been converted | 7/25/2019 - maw - I get a 403 - forbidden: Access is denied.
436 | Mark | Regional |  | Qa | RegSan | Custom |  | http://regionalsanqa.saccounty.net/ |  | 9/3/2019 - 403.14 - ** Talk to Shabab
432 | Mark | Regional |  | Prod | RegSan.Calendar | Custom |  | http://regionalsan.saccounty.net/events/TeamCalendar/TeamCalendar.asp |  | 9/3/2019 - works - http://regionalsan.saccounty.net/events/TeamCalendar/TeamCalendar.asp
437 | Mark | Regional |  | Qa | RegSan.OffsiteStorage | Custom |  | http://regionalsanqa.saccounty.net/OffsiteStorage |  | 9/3/2019 - works - http://regionalsanqa.saccounty.net/OffsiteStorage
419 | Mark | Regional |  | Prod | RegSan.WIMS | SSRS |  | http://mpsrsl01/reports_ssrs2016/browse/WIMS |  | 9/3/2019 - works - http://mpsrsl01/reports_ssrs2016/browse/WIMS
467 | Mark | Sasd | 2 | Dev | Resource Book | Custom | sasddiis1 | https://sasdebookdev.saccounty.net/ |  | 9/3/2019 - 503 - Service Unavailable - https://sasdebookdev.saccounty.net/ *** Open Ticket | Works * Facilies S001 - takes you to bad website. * Other Contacts - Water Perveyor CSD1 Overlay Map - takes you to a bad website. * Customer Phone List - Is creating CSV successfully. * Standby List - 2 links - one works, one error. * Administration - several links give me security errors. (Facilities other - create pdf file) |  | 4 - Mark tests websites that have been converted | 8/12/2019 - sasdapps-19
466 | Mark | Sasd |  | Prod | Resource Book | Custom | sasdpiis1 | http://sasdebook/ |  | 9/3/2019 - works - http://sasdebook/
25 | Shabab | Regional |  | Prod | RFI | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/rfi/ |  | 9/3/2019 - works - http://regionalsan.saccounty.net/rfi/
249 | Pedro | Regional |  |  | RSD-TIIS01 - DEV
285 | Pedro | Regional |  | Prod | rsp-iis01 | oob | rsp-iis01 | http://rsp-iis01/ |  | 9/3/2019 - works - default page
296 | Pedro | Regional |  |  | rsp-tfs01 | oob | http://rsp-tfs01/ |  |  | 9/3/2019 - works - demo page
267 | Pedro | Regional |  | QA | rsq-iis01 | oob | rsq-iis01 | http://rsq-iis01/ |  | 9/3/2019 - works - demo page
272 | Pedro | Regional |  | QA | rsqlimsapp01 | Vended | rsqlimsapp01 | http://rsqlimsapp01/SignIn?ReturnUrl=%2f |  | 9/3/2019 - works - horizon login page
116 | Tracey | SDA |  | Dev | Business Analyst Website | Custom | sasddiis1 | http *:80:sasdbadev, http *:80:sasdbadev.cospub.saccounty.net |  | 9/3/2019 - works - https://sasdbadev.saccounty.net/
550 | Mark | Regional |  | prod | sasd.BudgetP | Custom | sasdpiis1 | http://srwtp.saccounty.net/budgetcsd1/ActualsReports/CCReport.asp?cdcstcntr=3005020000 |  | 9/3/2019 - works - http://srwtp.saccounty.net/budgetcsd1/ActualsReports/CCReport.asp?cdcstcntr=3005020000 - passes user to home page
485 | Mark | Sasd | 2 | Dev | Metrics - Jason | Custom | sasddiis1 | http://sasdmetricsdev/ |  | 9/3/2019 - works - https://sasdmetricsdev.saccounty.net/ | 6/20 - sent message to Jason - itsec-547 | Jason | 6 - website converted successfully to https | 8/12 - sasdapps-19 |  | https://sasdmetricsdev.saccounty.net/
453 | Mark | Sasd |  | Dev | sasd.GIS | Custom |  | http://sasddgis1.cospub.saccounty.net:6080/arcgis/rest/services |  | 9/3/2019 - works - http://sasddgis1.cospub.saccounty.net:6080/arcgis/rest/services
477 | Mark | Sasd | 2 | Dev | Maximo Max2Gnet | Custom | sasddiis1 | http://sasdmax2gnetdev |  | 9/3/2019 - works - https://sasdmax2gnetdev.saccounty.net/ | Works - http://sasdmax2gnetdev.cospub.saccounty.net/default.aspx?wonum=1014802&anum=&op=3&hname=sasddmxapp1.cospub.saccounty.net | website comes up, but wants to redirect to GNET which doesn't work because I do not have GNET installed. *** maximo - launch in context integration, needs the extended url when moving to the QA instance. | 4 - Mark tests websites that have been converted | 8/12 - conversion complete?
493 | Mark | Sasd | 2 | Dev | NewHire | Custom | sasddiis1 | http://sasdnewhiredev/Tasks.aspx |  | 9/3/2019 - works - https://sasdnewhiredev.saccounty.net/new.aspx - *** Tasks - triggers cospub\sasdnewhiredev is not able to access database Inventory under current security context | Works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-16, sasdapps-19 |  | https://sasdnewhiredev.saccounty.net/new.aspx
510 | Mark | Sasd |  | Dev | sasd.SewerScoop | Custom | sasddiis1 | http://sasdsewerscoopdev/ | Static | 9/11 - works | 6/20 - sent message to Marjorie - itsec-547 | 6/25 - Awaiting reply from Marjories | 6 - converted successfully to https |  |  | https://sasdsewerscoopdev.saccounty.net/
100 | Tracey | Sasd |  | QA | sasd.SewerScoop | Custom | sasddiis1 | http *:80:sasdsewerscoopqa.cospub.saccounty.net, http *:80:sasdsewerscoopqa |  | 9/3/2019 - works - http://sasdsewerscoopqa/ - "Hello World"
520 | Mark | Sasd |  | Dev | sasd.Vault | Vended | sasddiis1 | http://sasdvaultservicedev/ |  | 9/3/2019 - works - directory - http://sasdvaultservicedev/
504 | Mark | Sasd |  | Prod | SCADA | Vended | sasdpiis1 | http://sasdscadaweb.saccounty.net/logon?redir=%2f |  | 9/3/2019 - works - login page | Meridian
115 | Tracey | Regional | 2 | Dev | Scapo | Custom | sasddiis1 | http *:80:sasdscapodev, http *:80:sasdscapodev.cospub.saccounty.net |  | 9/3/2019 - works - https://sasdscapodev.saccounty.net/ |  |  | 4 - Mark tests websites that have been converted
63 | Tracey | Sasd |  | Prod | Scapo | Custom | sasdpiis1 | http *:80:sasdscapo, http *:80:sasdscapo.cospub.saccounty.net |  | 9/3/2019 - http://sasdscapo/ - 403 - forbidden: Access is denied
117 | Tracey | Sasd |  | QA | Scapo | Custom | sasddiis1 | http *:80:SasdScapoTest, http *:80:SasdScapoTest.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdscapotest/
27 | Shabab | Regional |  |  | Scorecard | Vended |  | \\pwnr2\srwtpfolders\SRWTP Intranet\PB Views\Index.html |  | 9/3/2019 - works - \\pwnr2\srwtpfolders\SRWTP Intranet\PB Views\Index.html
98 | Tracey | Sasd | 2 | Dev | SDA BITS (Business Initiatives) | Custom | sasddiis1 | http *:80:sdabitsdev, http *:80:sdabitsdev.cospub.saccounty.net | 4.6.1 | 9/3/2019 - Telerik error |  |  | 4 - Mark tests websites that have been converted
531 | Mark | SDA | 2 | Dev | SDA BITS (Business Initiatives) | Custom | sasddiis1 | http://sdabitsdev/ | 4.6.1 | 9/3/2019 - Telerik error | 2 + dashboards work also |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-27
28 | Shabab | SDA |  | Prod | SDA BITS (Business Initiatives) | Custom | sasdpiis2 | http://sdabits/bits_inits_list.aspx?InitStatusID=6&DeptID=&SectionID=&GroupID= | 4.6.1 | 9/3/2019 - works - http://sdabits/bits_inits_list.aspx?InitStatusID=6&DeptID=&SectionID=&GroupID=
55 | Tracey | Sasd |  | Prod | SDA BITS (Business Initiatives) | Custom | sasdpiis1 | http *:80:SDABITS, http *:80:SDABITS.cospub.saccounty.net | 4.6.1 | 9/3/2019 - works - http://sdabits/bits_inits_list.aspx?InitStatusID=6&DeptID=&SectionID=&GroupID=
114 | Tracey | SDA |  | QA | SDA BITS (Business Initiatives) | Custom | sasddiis1 | http *:80:sdabitstest.cospub.saccounty.net, http *:80:sdabitstest | 4.6.1 | 9/3/2019 - works - UNTIL you navigate to Support Dashboard - then you get a error |  | sda Bits QA
534 | Mark | SDA | 1 | Dev | sda.DCS.Web | Custom | sasddiis1 | http://sdadcsdev/contractsearch.aspx |  | 9/3/2019 - Works - http://sdadcsdev/ | Works |  | 6 - website has been converted successfully to https | 7/25/2019 - maw - looks like it's still an http website.
532 | Mark | SDA |  | Prod | sda.DCS.Web | Custom |  | http://sdadcs/ | 3.5 | 9/3/2019 - works - http://sdadcs.saccounty.net/ |  |  | 6 - website has been converted successfully to https
535 | Mark | SDA |  | QA | sda.DCS.Web | Custom | sasddiis1 | http://SdaDcsQa | 3.5 | 9/3/2019 - works - http://SdaDcsQa |  |  | 6 - website has been converted successfully to https
304 | Mark | SDA |  | Prod | sda.Jira |  |  | http://10.94.242.84:8080 |  | 9/3/2019 - works - http://10.94.242.84:8080/secure/Dashboard.jspa
132 | Tracey | Regional |  | Dev | SDAD-MERIDIAN | Vended | RSD-TIIS01 | http://sdad-meridian/ |  | 9/3/2019 - works - login page - http://sdad-meridian/
133 | Tracey | Regional |  | Dev | SDAD-MERIDIAN | Vended | RSD-TIIS01 | http://sdad-bp/ |  | 9/3/2019 - 403 - Forbidden: Access is denied
261 | Pedro | SDA |  | Dev | SDAD-MERIDIAN | Vended | SDAD-MERIDIAN
264 | Pedro | SDA |  | Dev | SDAD-MERIDIAN | Vended | SDAD-MERIDIAN
541 | Mark | SDA |  | Dev | SDAD-MERIDIAN | Vended |  | http://sdastage-ki.mksi-lms.net |  | 9/3/2019 - works - login page - http://sdastage-ki.mksi-lms.net/
279 | Pedro | SDA |  | QA | SDAD-MERIDIAN | Vended | sdaq-meridian |  |  | 9/3/2019 - works - login page - http://sdaq-meridian/Default.aspx
540 | Mark | SDA |  | Qa | SDAD-MERIDIAN | Vended |  | http://sdaq-meridian |  | 9/3/2019 - works - login page - http://sdaq-meridian/Default.aspx
302 | Pedro | SDA |  | Prod | SDAP-bp | Vended | sdap-meridian
300 | Pedro | SDA |  | Prod | SDAP-ki | Vended | sdap-meridian
301 | Pedro | SDA |  | Prod | SDAP-ks | Vended | sdap-meridian
299 | Pedro | SDA |  | Prod | sdap-meridian | Vended | sdap-meridian | http://sdap-meridian/Default.aspx |  | 9/3/2019 - works - http://sdap-meridian/Default.aspx
276 | Pedro | SDA |  | QA | sdaq-meridian | Vended | sdaq-meridian |  |  | 9/3/2019 - works - login page - http://sdaq-meridian/Default.aspx
537 | Mark | SDA |  | Dev | SQL Reporting Services | Vended |  | http://SDAD-SRS01:80/Reports |  | 9/3/2019 - works
539 | Mark | SDA |  | Prod | srcsd.TFS | Vended | sasdpiis1 | http://sdap-tfs01:8080/tfs |  | 9/3/2019 - Cant reach this page - http://sdap-tfs01:8080/tfs
438 | Mark | Regional |  |  | srcsd.TFS | TFS |  | http://rsp-tfs01:8080/tfs |  | 9/3/2019 - works - http://rsp-tfs01:8080/tfs - TFS server
552 | Mark | Regional |  | prod | srwtp | Custom | sasdpiis1 | http://srwtp.saccounty.net/mgmt/ |  | 9/3/2019 - works - srwtp home page
1 | Shabab | Regional |  | Prod | SRWTP Events | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/events/default.asp |  | 9/3/2019 - works
156 | Tracey | Regional |  | Prod | SRWTP Redirect | Custom | RSP-IIS01 | srwtp.saccounty.net, srwtp
157 | Tracey | Regional |  | Prod | Struxure | Custom | RSP-IIS01 | *:82
29 | Shabab | Regional |  | Prod | Suggestion Program | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/suggestion/default.asp |  | 9/3/2019 - works
30 | Shabab | Regional |  | Prod | Supervisors Page | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/mgmt/ |  | 9/3/2019 - works - executive information system
101 | Tracey | Sasd |  | Dev | Survey | Custom | sasddiis1 | http *:80:sasdsurveydev, http *:80:sasdsurveydev.cospub.saccounty.net |  | 9/3/2019 - login failed for user CosPub\sasdsurveydev - http://sasdsurveydev/ *** Create a ticket to have this looked at
56 | Tracey | Sasd |  | Prod | Survey | Custom | sasdpiis1 | http *:80:sasdsurvey, http *:80:sasdsurvey.cospub.saccounty.net |  | 9/3/2019 - works
297 | Pedro | Regional |  |  | Team Foundation Server | oob | rsp-tfs01 |  |  |  |  | Cognos as the plant
517 | Mark | Sasd | 2 | Dev | Timesheet | Custom | sasddiis1 | http://sasdtimesheetv2dev.saccounty.net/Timesheet_v2.aspx | 4.6.1 | 9/3/2019 - this webpage cannot be found - https://sasdtimesheetv2dev.saccounty.net/Timesheet_v2.aspx - *** Ticket Needed | Works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-24
31 | Shabab | Regional |  | Prod | Timesheet - Regional san | Custom | RSP-IIS01 | http://regionalsan.saccounty.net/tsSRWTP/default.asp | asp | 9/3/2019 - timesheet login
62 | Tracey | Sasd |  | Prod | Timesheet | Custom | sasdpiis1 | http *:80:sasdtimesheet.cospub.saccounty.net, http *:80:sasdtimesheet | 4.6.1 | 9/3/2019 - works - http://sasdtimesheet.cospub.saccounty.net/Timesheet_v2.aspx
516 | Mark | Sasd |  | QA | Timesheet | Custom | sasddiis1 | http://sasdtimesheettest/Timesheet_v2.aspx | 4.6.1 | 9/3/2019 - works - http://sasdtimesheettest/Timesheet_v2.aspx
103 | Tracey | Sasd | 2 | Dev | Timesheet v2 | Custom | sasddiis1 | http *:80:sasdtimesheetv2dev, http *:80:sasdtimesheetv2dev.cospub.saccounty.net | 4.6.1 | 9/3/2019 - redbar - https://sasdtimesheetv2dev/Timesheet_v2.aspx |  |  | 4 - Mark tests websites that have been converted
57 | Tracey | Sasd |  | Prod | Timesheet v2 | Custom | sasdpiis1 | http *:80:sasdtimesheetv2, http *:80:sasdtimesheetv2.cospub.saccounty.net | 4.6.1 | 9/3/2019 - works - http://sasdtimesheet.cospub.saccounty.net/Timesheet_v2.aspx
104 | Tracey | Sasd |  | QA | TimesheetTest | Custom | sasddiis1 | http *:80:sasdTimesheetTest, http *:80:sasdTimesheettest.cospub.saccounty.net | 4.6.1 | 9/3/2019 - works - http://sasdtimesheettest/Timesheet_v2.aspx
105 | Tracey | Sasd |  | Dev | Uniform | Custom | sasddiis1 | http *:80:sasduniformdev, http *:80:sasduniformdev.cospub.saccounty.net |  | 9/3/2019 - login filed for user nt authority\anonymous logon
58 | Tracey | Sasd |  | Prod | Uniform | Custom | sasdpiis1 | http *:80:sasduniform, http *:80:sasduniform.cospub.saccounty.net |  | 9/3/2019 - works - http://sasduniform/
519 | Mark | Sasd |  | Dev | Uniform Tracking | Custom | sasddiis1 | http://sasduniformdev/home.aspx |  | 9/3/2019 - login filed for user nt authority\anonymous logon - http://sasduniformdev/home.aspx | Login failed for user 'NT AUTHORITY\ANONYMOUS LOGON'. | I sent a message to louella for more information
518 | Mark | Sasd |  | Prod | Uniform Tracking | Custom | sasdpiis1 | http://sasduniform/home.aspx |  | 9/3/2019 - works - http://sasduniform/home.aspx | Meridian
113 | Tracey | Sasd |  | Dev | Vaultweb | Vended | sasddiis1 | http *:80:sasdvaultservicedev.cospub.saccounty.net, http *:80:sasdvaultservicedev
106 | Tracey | Sasd |  | Dev | Wachdorf | Custom | sasddiis1 | http *:80:sasdwachdorfdev, http *:80:sasdwachdorfdev.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdwachdorfdev/
526 | Mark | Sasd | 2 | Dev | WSCS DMS | Custom | sasddiis1 | http://sasdwscsdmsdev/ |  | 9/3/2019 - works - https://sasdwscsdmsdev.saccounty.net/ | Works |  | 6 - website converted successfully to https | 8/12 - sasdapps-26 |  | https://sasdwscsdmsdev.saccounty.net/
525 | Mark | Sasd |  | Prod | WSCS DMS | Custom | sasdpiis1 | http://sasdwscsdms/ |  | 9/3/2019 - works - http://sasdwscsdms/ | Meridian
527 | Mark | Sasd |  | QA | WSCS DMS | Custom | sasddiis1 | http://sasdwscsdmsqa/ |  | 9/3/2019 - works - http://sasdwscsdmsqa/
528 | Mark | Sasd | 2 | Dev | wscs.MRP(p4) | Custom | sasddiis1 | http://sasdwscsmrpdev/ |  | 9/3/2019 - works - https://sasdwscsmrpdev.saccounty.net/ | Works |  | 6 - website converted successfully to https | 8/12 - sasdapps-17
61 | Tracey | Regional |  | Prod | wscs.MRP(p4) | Custom | sasdpiis1 | http *:80:sasdWscsMrp, http *:80:sasdwscsmrp.cospub.saccounty.net |  | 9/3/2019 - works - https://sasdwscsmrp.saccounty.net/ |  |  | 6 - website converted successfully to https
112 | Tracey | Regional |  | QA | wscs.MRP(p4) | Custom | sasddiis1 | http *:80:sasdWscsMrpQa, http *:80:sasdWscsMrpQa.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdwscsmrpqa/
529 | Mark | Sasd |  | QA | wscs.MRP(p4) | Custom | sasddiis1 | http://sasdwscsmrpqa/ |  | 9/3/2019 - works - http://sasdwscsmrpqa/
107 | Tracey | Regional | 2 | Dev | WscsCson | Custom | sasddiis1 | http *:80:sasdWscsCsonDev, http *:80:sasdWscsCsonDev.cospub.saccounty.net |  | 9/3/2019 - works - *** Configuration Error *** https://sasdwscscsondev.saccounty.net/ServerIdError.htm |  |  | 4 - Mark tests websites that have been converted
523 | Mark | Sasd | 2 | Dev | WscsCson | Custom | sasddiis1 | http://SasdWscsCsonDev |  | 9/3/2019 - works - *** Configuration Error *** https://sasdwscscsondev.saccounty.net/ServerIdError.htm | Works |  | 4 - Mark tests websites that have been converted | 8/12 - sasdapps-25
2 | Shabab | Regional |  | Prod | WscsCson | Custom | SASD IIS Server | http://sasdwscscson/ |  | 9/3/2019 - works - http://sasdwscscson/
59 | Tracey | Regional |  | Prod | WscsCson | Custom | sasdpiis1 | http *:80:sasdWscsCson, http *:80:sasdWscsCson.cospub.saccounty.net, http *:80:cson |  | 9/3/2019 - works - http://sasdwscscson/
551 | Mark | Regional |  | Prod | WscsCson | Custom | sasdpiis1 | http://srwtp.saccounty.net/collectionsystemeventscalendar/ |  | 9/3/2019 - passes user to srcsd home page. http://srwtp.saccounty.net/collectionsystemeventscalendar/
108 | Tracey | Regional |  | QA | WscsCson | Custom | sasddiis1 | http *:80:sasdWscsCsonQa, http *:80:sasdWscsCsonQa.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdwscsmrpqa/
524 | Mark | Sasd |  | QA | WscsCson | Custom | sasddiis1 | http://SasdWscsCsonQa/ |  | 9/3/2019 - works - http://sasdwscsmrpqa/
60 | Tracey | Regional |  | Prod | WscsDms | Custom | sasdpiis1 | http *:80:sasdWscsDms, http *:80:sasdwscsdms.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdwscsdms/Inventory/Inventory_Home.aspx
191 | Pedro | Regional |  | Prod | WscsDms | Custom | sasdpiis1 |  |  | 9/3/2019 - works - default home page
110 | Tracey | Regional |  | QA | WscsDmsQa | Custom | sasddiis1 | http *:80:sasdWscsDmsQa, http *:80:sasdWscsDmsQa.cospub.saccounty.net |  | 9/3/2019 - works - http://sasdwscsdmsqa/Inventory/Inventory_Home.aspx