## Instructions
Project Level Assessment Tool
Background
The Project Level Assessment is a 24-question assessment that determines the risk and complexity of a project and then assigns a Level of 1, 2, or 3 to the project.
Projects are assigned a level based on a combination of three elements: - Level thresholds for each risk category, which determine how a project is scored for a specific category (e.g. Scope, Time, Cost, Quality, etc.). These are set once for all projects. - Importance weightings for each risk category, for a specific project, which determine how much a score for one category impacts the overall project level. - Responses to the 24 questions.
Each question is associated with one or more project risk categories, and the answer you choose will impact the project's score for those categories. The category thresholds are set manually in the Level Thresholds tab. The actual project level is determined by the importance rating for all categories.
This tool contains the following: 1) Instructions - (This page) provides information on the tool itself. 2) Level Thresholds - This tab allows for level thresholds to be set for each risk category. This tab will be completed once according to the thresholds set by your Project Management organization. Note: once completed, hide this tab to avoid confusion. 3) Project x Input - These tabs allow for weighting of the categories by importance, and contain the assessment questions to be answered for each project. Up to 3 projects can be assessed (Project 1 Input, Project 2 Input, Project 3 Input). 4) Project x Results - These tabs present the results of the assessment, including which risk categories are of greater or lesser concern to the project as a whole. Each project will have its own results page. The results for up to 3 projects can be generated. (Project 1 Results, Project 2 Results, Project 3 Results).
ð The tool is designed to determine the project level as follows: Level 1: Lowest risk, least complex Level 2: Moderate risk and complexity Level 3: Highest risk and complexity
Reference documents
PMBOK® Guide Fifth Edition
For acceptable use of this tool, refer to Info-Tech's Terms of Use. These documents are intended to supply general information only, not specific professional or personal advice, and are not intended to be used as a substitute for any kind of professional advice. Use this document either in whole or in part as a basis and guide for document creation. To customize this document with corporate marks and titles, simply replace the Info-Tech information in the Header and Footer fields of this document.

## Level Thresholds
Project Level Thresholds
For each risk category, set thresholds that will determine the project level for that category. Exceeding the threshold does not automatically move the entire project up to the next level - the project level is also determined by the risk category importance weightings assigned on the Project Input tab. Instructions: Assign ranges for each risk category. The upper and lower percentages for each category set the threshold for that particular category and will determine how the project is scored for that category. E.g. If the Level 1 threshold for Scope Risks is in the 0-25% range, then a project would have to score below 25% on Scope for that category to be given a Level 1 score.
| Risk Category | Level 1 |  |  | Level 2 |  |  | Level 3
1.1 | Scope Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.2 | Time Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.3 | Cost Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.4 | Quality Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.5 | Human Resources Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.6 | Communications Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.7 | Procurement Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%
1.8 | Stakeholder Risks | 0% | − | 40% | 41% | − | 70% | 71% | − | 100%

## Project 1 Input
Project Level Assessment
| Project Name | Initiative-6 - HTTP 2 HTTPS - Conversion to SSL
| Project Description | Convert ISD, RegionalSan and SASD websites from HTTP to HTTPS thus securing those websites.
| Project Type | Business Process Inititiative
| Project Status | Initiation
| Risk Category | Importance
1.1 | Scope Risks | 25% | These weightings should be set by the Project Manager to reflect the importance of different risk categories to the overall success of the project.
1.2 | Time Risks | 15%
1.3 | Cost Risks | 20%
1.4 | Quality Risks | 10%
1.5 | Human Resources Risks | 5%
1.6 | Communications Risks | 5%
1.7 | Procurement Risks | 10%
1.8 | Stakeholder Risks | 10%
|  | 100% | Note: Total must equal 100%
| Question | Options | Risk Categories
1 | What is the total budget for this project? | $0 - $10,000 | Cost
2 | What percentage of the overall project budget is for procurement? | No procurement is required | Cost, Procurement
3 | How would you describe the size of the budget relative to other projects in your organization? Note: Total budget includes capital and operating costs. | Small | Cost
4 | What is the estimate for the number of resources required to complete this project? Note: Resources include full-time and part-time staff, as well as contractors, consultants and vendors. | < 10 | HR, Time
5 | What is the estimated duration of the project ? | 12-24 months | Time, Scope, Cost
6 | What parts of the organization will this project impact? | The entire organization | Communication, HR, Scope
7 | Does the project align with business objectives? | The project directly aligns with one or more business objectives. | Stakeholder, Scope
8 | Do the business benefits of the project provide value to the organization? | The business benefits are compelling, and the value is clearly understood and documented. | Stakeholder, Scope
9 | Are key stakeholders engaged in the early stages of project planning? | All key stakeholders are identified, engaged and consulted during early project planning. | Stakeholder, Communications, Scope
10 | What type of communication plan will be required? | Simple communication plan, with a few key stakeholders. | Stakeholder, Communications
11 | How would you characterize the commitment of senior management to the project? | All business and IT stakeholders are fully committed to and engaged in the project. | Stakeholder, Scope
12 | How available are required vendors or suppliers? | There are many vendors that can satisfy procurement requirements or no procurement is required. | Procurement, Cost, Time
13 | How many separate vendor contracts will be required for this project? | One contract; or no procurement is required. | Procurement, Cost
14 | Do you anticipate resource or skillset constraints with the project? | Required skillsets are expected to be tight in terms of availability. | HR, Time, Cost, Quality
15 | How do you expect team workload allocation to impact project timelines? | Team members are part-time on the project but have the required availability. Team workload presents minor risk to the project timeline. | HR, Time, Cost, Quality
16 | What prior experience does the project team possess with regards to this type of project? | This project has been done before by the organization. | HR, Time, Cost, Quality, Scope
17 | Has the assigned Project Manager worked on a project of this size and complexity before? | Yes | HR, Time, Cost, Quality, Scope
18 | Does the project require an organizational change management plan? | There are no significant change management requirements. | HR, Communications, Time, Cost
19 | What is the level of customer involvement required for this project? | Limited customer involvement is required for project success. | Stakeholder, Communications, Time, Quality
20 | Are project requirements clear and documented? | Less than 50% of total requirements are clearly articulated and documented. | Scope, Communications
21 | Are project requirements expected to remain stable? | All project requirements are expected to remain stable. | Scope, Communications, Time, Cost, Quality
22 | Are any other projects dependent on the outputs or outcomes of this project? | No | Scope, Quality, Time,
23 | Is this project dependent on the outputs or outcomes of any other projects? | No | Time, Cost, Quality
24 | What degree of integration with other projects, systems, infrastructure, or organizations is required (i.e. integration with things external to the project)? | There are a few integration requirements. | Time, Cost, Communications

## Hidden - Drop Down Lookup (hidden)
Dollars | Score
$0 - $10,000 | 1
$10,000 - $25,000 | 2
$25,000 - $50,000 | 3
$50,000 - $100,000 | 4
> $100,000 | 5
Procurement
No procurement is required | 1
< 25% | 2
26% - 50% | 3
51% - 75% | 4
> 75% | 5
Size
Small | 1
Medium | 3
Large | 5
Range
< 10 | 1
10-20 | 2
20-40 | 3
40-60 | 4
>60 | 5
Months
< 3 months | 1
3-6 months | 2
6-12 months | 3
12-24 months | 4
> 24 months | 5
BusProc
A single business process | 1
Multiple business processes | 2
Multiple functions or departments | 3
Multiple locations | 4
The entire organization | 5
Project
No the project is not susceptible | 1
Yes, the project is moderately susceptible; time delays will have minor effects on the schedule. | 3
Yes, the project is highly susceptible; time delays will have major effects on the schedule. | 5
Statement2
Neither statement applies | 1
One statement is true | 3
Both statements are true | 5
YesNo
Yes | 5
No | 1
ProjAlign
The project directly aligns with one or more business objectives. | 1
The project indirectly contributes to one or more business objectives. | 3
The project does not clearly contribute to one or more business objectives. | 5
BusBen
The business benefits are compelling, and the value is clearly understood and documented. | 1
The business benefits seem to provide some value, but further clarification is required. | 3
The business benefits do not provide value or are not well understood and documented. | 5
ProjRel
All key stakeholders are identified, engaged and consulted during early project planning. | 1
Stakeholders are identified, but not fully engaged or consulted during early project planning. | 3
Stakeholders have not been identified or engaged during early project planning. | 5
ComPoint
Simple communication plan, with a few key stakeholders. | 1
Multiple stakeholders, with different information requirements. | 3
Many stakeholders, both internal and external, that need frequent communication in a variety of formats. | 5
Criteria4
All business and IT stakeholders are fully committed to and engaged in the project. | 1
A project champion is engaged at the senior management level. | 2
A project sponsor is identified and fully engaged in the project. | 3
There is a project sponsor, but this person is engaged in other projects and activities. | 4
There is no project sponsor and no clearly identifiable executive commitment. | 5
ProjReq
Completely addresses all project requirements; or no procurement is required. | 1
Is high-level and adequately describes required procurement activities. | 3
Only has rough details; or completed document is inappropriate for the project. | 5
Bidder
There are many vendors that can satisfy procurement requirements or no procurement is required. | 1
There is a limited number of qualified vendors or suppliers. | 3
There is only one qualified vendor or there are no qualified vendors that can meet procurement requirements. | 5
Supply
Yes: products, goods, or services can be readily supplied; or no procurement is required. | 1
There may be potential slippage of project schedule due to procurement complexity or vendor challenges. | 3
The project deliverables, schedule, or budget may be seriously affected by limited qualified bidders, significant request-for-proposal (RFP) process delays, or extended challenges. | 5
Statement3
All statements are true; or no procurement is required. | 1
Two statements are true. | 2
One statement is true. | 4
None of the statements are true. | 5
Contract
One contract; or no procurement is required. | 1
2-5 contracts | 3
> 5 contracts | 5
Require
All requirements are clearly articulated and documented. | 1
At least 50% of total requirements are clearly articulated and documented. | 3
Less than 50% of total requirements are clearly articulated and documented. | 5
Criteria3
Required skillsets are expected to be available for the duration of the project. | 1
Some turnover is expected, but a suitable replacement is expected to be available on short notice. | 3
Required skillsets are expected to be tight in terms of availability. | 5
Team
Team members will be fully allocated to the project. Team workload presents no risk to the project timeline. | 1
Team members are part-time on the project but have the required availability. Team workload presents minor risk to the project timeline. | 3
Some or all of the team members are over-committed. Team workload presents serious risks to the project timeline. | 5
Knowledge
This project has been done before by the organization. | 1
This project has not been done before, but has a proven approach. | 3
This is a new type of project for the organization and has not been proven. | 5
ManReq
There are no significant change management requirements. | 1
A basic change management plan is required. Minor changes to job roles and reporting relationships will occur. | 3
Significant change management will be required. There will be considerable changes to organizational structure. | 5
Customer
No customer involvement is required for project success. | 1
Limited customer involvement is required for project success. | 2
Moderate customer involvement is required for project success. | 4
Extensive customer involvement is required for project success. | 5
Conform
The project fully conforms with all applicable policies. Alternatively, the project is not subject to any of these policies. | 1
There are some challenges associated with policy requirements, but the project does not need to be structured around the policies. | 3
The project must be structured around meeting the policy requirements. | 5
Statement
Four of the statements are true | 1
Three of the statements are true | 2
Two of the statements are true | 3
One of the statements is true | 4
None of the statements are true | 5
Integration
There are a few integration requirements. | 1
There are a moderate number of integration requirements. | 3
There are many integration requirements. | 5
ProjReq2
All project requirements are expected to remain stable. | 1
Most project requirements are expected to remain stable. | 2
Some project requirements are expected to change after the project is launched. | 3
Many of the project requirements are expected to change during the lifetime of the project. | 4
Project requirements are expected to be highly unstable during the lifetime of the project. | 5
This is an area with a higher level of risk. Consider using a higher level of management here.
You have a lower level of risk in this area.

## Project 1 Results
Project Level Results
This is a Level 1 project
Risk Category | Rating | Notes | % of Overall Project Risk
Scope Risks | 41.51% | This is an area with a higher level of risk. | 37.04%
Time Risks | 35.94% |  | 11.11%
Cost Risks | 34.33% |  | 14.81%
Quality Risks | 38.46% |  | 7.407%
Human Resources Risks | 50% | This is an area with a higher level of risk. | 7.407%
Communications Risks | 42.5% | This is an area with a higher level of risk. | 7.407%
Procurement Risks | 23.08% |  | 7.407%
Stakeholder Risks | 25% |  | 7.407%

## HIDE Logic 1 (hidden)
Score
1
1 | [5 empty] | Do Not Edit this table - edit the grey cells on the "Level Thresholds" tab
1 | 0 | Risk Category | Level 1 |  |  | Level 2 |  |  | Level 3 |  |  | Score | Level |  | Importance Weighting
1 | 1.1 | Scope Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 41.51% | Level 2 | 2 | 25% | 0.5
4 | 1.2 | Time Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 35.94% | Level 1 | 1 | 15% | 0.15
5 | 1.3 | Cost Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 34.33% | Level 1 | 1 | 20% | 0.2
1 | 1.4 | Quality Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 38.46% | Level 1 | 1 | 10% | 0.1
1 | 1.5 | Human Resources Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 50% | Level 2 | 2 | 5% | 0.1
1 | 1.6 | Communications Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 42.5% | Level 2 | 2 | 5% | 0.1
1 | 1.7 | Procurement Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 23.08% | Level 1 | 1 | 10% | 0.1
1 | 1.8 | Stakeholder Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 25% | Level 1 | 1 | 10% | 0.1
1 |  | Overall Project Level | [9 empty] | 36.35% |  | 1 | 100% | 1.35
1 | [13 empty] | 11 |  | 17.5%
5 |  | Status
3
1 |  | Initiation | [5 empty] | Notes
1 |  | Planning | [5 empty] | This is an area with a higher level of risk.
1 |  | Execution | [5 empty] | You have a lower level of risk in this area.
2 |  | Close
5
1 |  | Project Type
1
1 |  | Infrastructure upgrade
1 |  | New application
42 |  | Business Process Inititiative

## Project 2 Input
Project Level Assessment
| Project Name | Maximo Purchasing
| Project Description | [Replace with project description that includes the goals of the project]
Project Type
Project Status
| Risk Category | Importance
1.1 | Scope Risks | 15% | These weightings should be set by the Project Manager to reflect the importance of different risk categories to the overall success of the project.
1.2 | Time Risks | 15%
1.3 | Cost Risks | 15%
1.4 | Quality Risks | 15%
1.5 | Human Resources Risks | 10%
1.6 | Communications Risks | 10%
1.7 | Procurement Risks | 10%
1.8 | Stakeholder Risks | 10%
|  | 100% | Note: Total must equal 100%
| Question | Options | Risk Categories
1 | What is the total budget for this project? | $50,000 - $100,000 | Cost
2 | What percentage of the overall project budget is for procurement? | 51% - 75% | Cost, Procurement
3 | How would you describe the size of the budget relative to other projects in your organization? Note: Total budget includes capital and operating costs. | Medium | Cost
4 | What is the estimate for the number of resources required to complete this project? Note: Resources include full-time and part-time staff, as well as contractors, consultants and vendors. | 10-20 | HR, Time
5 | What is the estimated duration of the project ? | > 24 months | Time, Scope, Cost
6 | What parts of the organization will this project impact? | Multiple functions or departments | Communication, HR, Scope
7 | Does the project align with business objectives? | The project directly aligns with one or more business objectives. | Stakeholder, Scope
8 | Do the business benefits of the project provide value to the organization? | The business benefits are compelling, and the value is clearly understood and documented. | Stakeholder, Scope
9 | Are key stakeholders engaged in the early stages of project planning? | Stakeholders are identified, but not fully engaged or consulted during early project planning. | Stakeholder, Communications, Scope
10 | What type of communication plan will be required? | Multiple stakeholders, with different information requirements. | Stakeholder, Communications
11 | How would you characterize the commitment of senior management to the project? | There is no project sponsor and no clearly identifiable executive commitment. | Stakeholder, Scope
12 | How available are required vendors or suppliers? | There is a limited number of qualified vendors or suppliers. | Procurement, Cost, Time
13 | How many separate vendor contracts will be required for this project? | One contract; or no procurement is required. | Procurement, Cost
14 | Do you anticipate resource or skillset constraints with the project? | Some turnover is expected, but a suitable replacement is expected to be available on short notice. | HR, Time, Cost, Quality
15 | How do you expect team workload allocation to impact project timelines? | Team members are part-time on the project but have the required availability. Team workload presents minor risk to the project timeline. | HR, Time, Cost, Quality
16 | What prior experience does the project team possess with regards to this type of project? | This is a new type of project for the organization and has not been proven. | HR, Time, Cost, Quality, Scope
17 | Has the assigned Project Manager worked on a project of this size and complexity before? | Yes | HR, Time, Cost, Quality, Scope
18 | Does the project require an organizational change management plan? | Significant change management will be required. There will be considerable changes to organizational structure. | HR, Communications, Time, Cost
19 | What is the level of customer involvement required for this project? | Extensive customer involvement is required for project success. | Stakeholder, Communications, Time, Quality
20 | Are project requirements clear and documented? | Less than 50% of total requirements are clearly articulated and documented. | Scope, Communications
21 | Are project requirements expected to remain stable? | Some project requirements are expected to change after the project is launched. | Scope, Communications, Time, Cost, Quality
22 | Are any other projects dependent on the outputs or outcomes of this project? | Yes | Scope, Quality, Time,
23 | Is this project dependent on the outputs or outcomes of any other projects? | Yes | Time, Cost, Quality
24 | What degree of integration with other projects, systems, infrastructure, or organizations is required (i.e. integration with things external to the project)? | There are a moderate number of integration requirements. | Time, Cost, Communications

## HIDE Logic 2 (hidden)
Score
4
4 | [5 empty] | Do Not Edit this table - edit the grey cells on the "Level Thresholds" tab
3 | 0 | Risk Category | Level 1 |  |  | Level 2 |  |  | Level 3 |  |  | Score | Level |  | Importance Weighting
2 | 1.1 | Scope Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 69.81% | Level 2 | 2 | 15% | 0.3
5 | 1.2 | Time Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 75% | Level 3 | 3 | 15% | 0.45
3 | 1.3 | Cost Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 71.64% | Level 3 | 3 | 15% | 0.45
1 | 1.4 | Quality Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 76.92% | Level 3 | 3 | 15% | 0.45
1 | 1.5 | Human Resources Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 64.71% | Level 2 | 2 | 10% | 0.2
3 | 1.6 | Communications Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 75% | Level 3 | 3 | 10% | 0.3
3 | 1.7 | Procurement Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 61.54% | Level 2 | 2 | 10% | 0.2
5 | 1.8 | Stakeholder Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 64.29% | Level 2 | 2 | 10% | 0.2
3 |  | Overall Project Level | [9 empty] | 69.86% |  | 3 | 100% | 2.55
1 | [13 empty] | 20 |  | 77.5%
3 |  | Status
3
5 |  | Initiation | [5 empty] | Notes
1 |  | Planning | [5 empty] | This is an area with a higher level of risk.
5 |  | Execution | [5 empty] | You have a lower level of risk in this area.
5 |  | Close
5
3 |  | Project Type
5
5 |  | Infrastructure upgrade
3 |  | New application
81 |  | Business Process Inititiative

## Project 2 Results
Project Level Results
This is a Level 3 project
Risk Category | Rating | Notes | % of Overall Project Risk
Scope Risks | 69.81% | You have a lower level of risk in this area. | 11.76%
Time Risks | 75% |  | 17.65%
Cost Risks | 71.64% |  | 17.65%
Quality Risks | 76.92% |  | 17.65%
Human Resources Risks | 64.71% | You have a lower level of risk in this area. | 7.843%
Communications Risks | 75% |  | 11.76%
Procurement Risks | 61.54% | You have a lower level of risk in this area. | 7.843%
Stakeholder Risks | 64.29% | You have a lower level of risk in this area. | 7.843%

## Project 3 Input
Project Level Assessment
| Project Name | [Replace with Project 3 Name]
| Project Description | [Replace with project description that includes the goals of the project]
| Project Type | IT Enabled
| Project Status | Initiation
| Risk Category | Importance
1.1 | Scope Risks | 15% | These weightings should be set by the Project Manager to reflect the importance of different risk categories to the overall success of the project.
1.2 | Time Risks | 15%
1.3 | Cost Risks | 15%
1.4 | Quality Risks | 15%
1.5 | Human Resources Risks | 10%
1.6 | Communications Risks | 10%
1.7 | Procurement Risks | 10%
1.8 | Stakeholder Risks | 10%
|  | 100% | Note: Total must equal 100%
| Question | Options | Risk Categories
1 | What is the total budget for this project? | $10,000 - $25,000 | Cost
2 | What percentage of the overall project budget is for procurement? | 26% - 50% | Cost, Procurement
3 | How would you describe the size of the budget relative to other projects in your organization? Note: Total budget includes capital and operating costs. | Medium | Cost
4 | What is the estimate for the number of resources required to complete this project? Note: Resources include full-time and part-time staff, as well as contractors, consultants and vendors. | 10-20 | HR, Time
5 | What is the estimated duration of the project ? | 6-12 months | Time, Scope, Cost
6 | What parts of the organization will this project impact? | Multiple functions or departments | Communication, HR, Scope
7 | Does the project align with business objectives? | The project indirectly contributes to one or more business objectives. | Stakeholder, Scope
8 | Do the business benefits of the project provide value to the organization? | The business benefits seem to provide some value, but further clarification is required. | Stakeholder, Scope
9 | Are key stakeholders engaged in the early stages of project planning? | Stakeholders have not been identified or engaged during early project planning. | Stakeholder, Communications, Scope
10 | What type of communication plan will be required? | Multiple stakeholders, with different information requirements. | Stakeholder, Communications
11 | How would you characterize the commitment of senior management to the project? | A project sponsor is identified and fully engaged in the project. | Stakeholder, Scope
12 | How available are required vendors or suppliers? | There is a limited number of qualified vendors or suppliers. | Procurement, Cost, Time
13 | How many separate vendor contracts will be required for this project? | 2-5 contracts | Procurement, Cost
14 | Do you anticipate resource or skillset constraints with the project? | Some turnover is expected, but a suitable replacement is expected to be available on short notice. | HR, Time, Cost, Quality
15 | How do you expect team workload allocation to impact project timelines? | Team members are part-time on the project but have the required availability. Team workload presents minor risk to the project timeline. | HR, Time, Cost, Quality
16 | What prior experience does the project team possess with regards to this type of project? | This project has not been done before, but has a proven approach. | HR, Time, Cost, Quality, Scope
17 | Has the assigned Project Manager worked on a project of this size and complexity before? | Yes | HR, Time, Cost, Quality, Scope
18 | Does the project require an organizational change management plan? | A basic change management plan is required. Minor changes to job roles and reporting relationships will occur. | HR, Communications, Time, Cost
19 | What is the level of customer involvement required for this project? | Moderate customer involvement is required for project success. | Stakeholder, Communications, Time, Quality
20 | Are project requirements clear and documented? | At least 50% of total requirements are clearly articulated and documented. | Scope, Communications
21 | Are project requirements expected to remain stable? | Some project requirements are expected to change after the project is launched. | Scope, Communications, Time, Cost, Quality
22 | Are any other projects dependent on the outputs or outcomes of this project? | No | Scope, Quality, Time,
23 | Is this project dependent on the outputs or outcomes of any other projects? | Yes | Time, Cost, Quality
24 | What degree of integration with other projects, systems, infrastructure, or organizations is required (i.e. integration with things external to the project)? | There are a moderate number of integration requirements. | Time, Cost, Communications

## HIDE Logic 3 (hidden)
Score
2
3 | [5 empty] | Do Not Edit this table - edit the grey cells on the "Level Thresholds" tab
3 | 0 | Risk Category | Level 1 |  |  | Level 2 |  |  | Level 3 |  |  | Score | Level |  | Importance Weighting
2 | 1.1 | Scope Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 58.49% | Level 2 | 2 | 15% | 0.3
3 | 1.2 | Time Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 57.81% | Level 2 | 2 | 15% | 0.3
3 | 1.3 | Cost Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 61.19% | Level 2 | 2 | 15% | 0.3
3 | 1.4 | Quality Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 58.97% | Level 2 | 2 | 15% | 0.3
3 | 1.5 | Human Resources Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 52.94% | Level 2 | 2 | 10% | 0.2
5 | 1.6 | Communications Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 67.5% | Level 2 | 2 | 10% | 0.2
3 | 1.7 | Procurement Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 69.23% | Level 2 | 2 | 10% | 0.2
3 | 1.8 | Stakeholder Risks | 0% | − | 40% | 40% | − | 70% | 70% | − | 100% | 75% | Level 3 | 3 | 10% | 0.3
3 |  | Overall Project Level | [9 empty] | 62.64% |  | 2 | 100% | 2.1
3 | [13 empty] | 17 |  | 55%
3 |  | Status
3
3 |  | Initiation | [5 empty] | Notes
1 |  | Planning | [5 empty] | This is an area with a higher level of risk.
3 |  | Execution | [5 empty] | You have a lower level of risk in this area.
4 |  | Close
3
3 |  | Project Type
1
5 |  | Infrastructure upgrade
3 |  | New application
71 |  | Business Process Inititiative

## Project 3 Results
Project Level Results
This is a Level 2 project
Risk Category | Rating | Notes | % of Overall Project Risk
Scope Risks | 58.49% |  | 14.29%
Time Risks | 57.81% |  | 14.29%
Cost Risks | 61.19% |  | 14.29%
Quality Risks | 58.97% |  | 14.29%
Human Resources Risks | 52.94% |  | 9.524%
Communications Risks | 67.5% |  | 9.524%
Procurement Risks | 69.23% |  | 9.524%
Stakeholder Risks | 75% | This is an area with a higher level of risk. | 14.29%